## 3rd June (2)
DEFECT
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
| CARESOURCE | GCCS-52547 | High | Issue | CM Document is missing from Guiding Care 6/01/2022 | IN CLIENT VALIDATION | Observations shared by Inbound Team. Waiting for feedback | Data Loads | N/A | N | 8.16.2022.03 | EST | CM | N/A | INBOUND | Anoop
| MEDICA | GCCS-52721 | Low | Issue | Config Store Import not working in QA | INVESTIGATING | Observations shared with L2 team | Configuration | Y | N | 8.15.2022.05 | EST | AG | N/A | L2 | Anoop
| MEDICA | GCCS-52938 | Low | Issue | INC1115405 authorization cannot be updated | INVESTIGATING | PS Team is working on this | DB | Y | N | 8.15.2022.05 | EST | UM | N/A | PS | Anoop
| PRIORITY HEALTH | GCCS-52937 | High | Issue | Issue Viewing Current Condition Note | INVESTIGATING | Observations shared with L2 team |  | Y | N | 8.14.2022.03 | EST | CM | N/A | L2 | Anoop
| VNS | GCCS-52930 | High | Issue | Activities are being delayed. | INVESTIGATING | Observationsshard with Client. Needed More Information |  | N | Y | 8.16.2022.03 | EST | CM | N/A | PS | Anoop
| CARE SOURCE | GCCS-52917 | Low | ISSUE | Please load CARESOURCE_AH_T_INCR_834_20220603073648.edi inr to PP1 | INVESTIGATING | Observations shared with Inbound team | INBOUND | N | Y | 8.16.2022.03 | EST | CM/UM | N/A | INBOUND | Naresh
| CARE SOURCE | GCCS-52549 | Low | ISSUE | Medical Claims File that we sent and didn't process 6/1/2022 7:30PM to 6/2/2022 7:30 PM | INVESTIGATING | Observations shared with Inbound team | INBOUND | N | Y | 8.16.2022.03 | EST | CM/UM | N/A | INBOUND | Naresh
| VNS | GCCS-52949 | CRITICAL | Issue | Member Eligibilities not showing in GuidingCare | INVESTIGATING | Observations shared with Inbound team | INBOUND | N | Y | 8.16.2022.03 | EST | CM | N/A | INBOUND | Naresh
| CARE SOURCE | GCCS-7555 | Low | ISSUE | The "Auth Priority" field on the Auth Entry screen should be editable when all non-voided, non-deleted rows on the auth are pending. | INVESTIGATING | PS Team is working on this | UPDATE request | N | Y | 8.16.2022.03 | EST | CM/UM | N/A | PS | Naresh
| DHMP | GCCS-52348 | HIGH | ISSUE | Incident of MCG notes crossing into other auths | Waiting for Customer | We have verified the same scenario at our end but we are unable to replicate the issue at our end. Please provide us with all the steps followed that lead to the issue and also share us with the Screenshot/ video Recording of the Issue. so that it would help us in investigating and take this to resolution? | Config | N | N | 8.11.0.M01 | MST | UM | N/A | PS | Arun
| MEDICA | GCCS-52950 | MEDIUM | ISSUE | INC1115294 user has to save several times to get auth to save in Guiding Care | IN PROGRESS | PS Team is working upon it. | CONFIG | N | N | 8.15.2022.02 | EST | UM | N/A | PS | Arun
| HEALTH ALLIANCE | GCCS-52955 | MEDIUM | ISSUE | Unable to generate letter for auth | IN PROGRESS | Shared the information with swat team for further analysis | CONFIG | Y | N | 8.14.2022.03 | EST | UM | N/A | SWAT-INDIA | Arun
| CARE SOURCE | GCCS-52956 | LOW | ISSUE | PROD: UM Auth Status Not Saving | IN PROGRESS | PS Team is working upon it. | CONFIG | N | N | 8.15.2022.02 | EST | UM | N/A | PS | Arun
| MED STAR | GCCS-51207 | LOW | ISSUE | Patch Release indicated activity due dates would appear in black--They appear to continue in red and yellow. | WAITING FOR CUSTOMER | Shared the information with client waiting for there response | CONFIG | N | N | 8.15.2022.03 | EST | AG | N/A | PS | Arun
STORY
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
TASK
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
| ICIRCLE | GCCS-52926 | Medium | Task | Script update: Ready to schedule | Open | PS Team is working on this | Sync Task | N/A | N | 8.13.4.2022.02 | EST | CM | N/A | PS | Anoop
| ICIRCLE | GCCS-52927 | Medium | Task | New activity: Follow up on NYIA scheduling | Open | PS Team is working on this | Sync Task | N/A | N | 8.13.4.2022.02 | EST | CM | N/A | PS | Anoop
1 | ICIRCLE | GCCS-52929 | Medium | Task | Script Change-Enrollment Community Intake Call | Open | PS Team is working on this | Sync Task | N/A | N | 8.13.4.2022.02 | EST | CM | N/A | PS | Anoop
| CARESOURCE | GCCS-52928 | Medium | Task | Please load CARESOURCE_AH_T_INCR_834_20220603003005.edi into PP1 | Open | Assigned to Inbound Team | Data Loads | N/A | N | 8.16.2022.03 | EST | CM | N/A | INBOUND | Anoop
| HEALTH ALLIANCE | GCCS-52931 | Medium | Task | Load Tapestry eligibility into Guiding Care | Open | Assigned to Inbound Team | Data Loads | N/A | N | 8.14.2022.03 | EST | UM | N/A | INBOUND | Anoop
| ICIRCLE | GCCS-52948 | MEDIUM | TASK | New Program Status names/descriptions | INVESTIGATING | PS team is working on the sync request | SYNC REQUEST | N/A | N | 8.13.4.2022.02 | EST | CM | N/A | PS | Naresh
| ALOHACARE | GCCS-52947 | MEDIUM | TASK | Add 3 new CM activity "Contact Types" | INVESTIGATING | Observations are shared with customer | Configuration | N/A | N | 8.16.2022.03 | HST | UM | N/A | PS | Naresh
| COA | GCCS-52943 | MEDIUM | TASK | Appointment Types and Statuses | IN PROGRESS | PS Team is working upon it. | DATA CHANGES | N | N | 8.13.4.2022.01 | EST | CM | N/A | PS | Arun
| CARE SOURCE | GCCS-52951 | MEDIUM | TASK | Confirm readiness to consume HIE-LAB *v2V and *v2L files | IN PROGRESS | Assigned to inbound team | INBOUND | N | N | 8.15.2022.02 | EST | INBOUND | N/A | INBOUND | Arun
| PRIORITY HEALTH | GCCS-52953 | MEDIUM | TASK | Script Details | IN PROGRESS | PS Team is working upon it. | DATA CHANGES | N | N | 8.14.2022.03 | EST | CM | N/A | PS | Arun
| VNS | GCCS-52957 | MEDIUM | TASK | Pending SCIC to be completed | IN PROGRESS | DB Team need to share the details | DATA CHANGES | N | N | 8.12.2022.01 | EST | CM | N/A | PS | Arun
| COA | GCCS-52958 | MEDIUM | TASK | Recover member data in GC Preprod | IN PROGRESS | DB Team need to share the details | DATA CHANGES | N | N | 8.13.4.2022.01 | EST | CM | N/A | PS | Arun
| ALOHACARE | GCCS-52959 | MEDIUM | TASK | List of providers to use in UM auth | IN PROGRESS | PS Team is working upon it. | DATA CHANGES | N | N | 8.13.4.2022.02 | HST | UM | N/A | PS | Arun
| CARE SOURCE | GCCS-52960 | MEDIUM | TASK | Production API monitoring and proactive resolution | IN PROGRESS | Assigned to Zach | API | N | N | 8.15.2022.02 | EST | API | N/A | SWAT-INDIA | Arun
Ad-Hocs
SL.NO | Client | Internal/ External | Description
| Aloha | INTERNAL | GCCS-51256 : Worked on Old Ticket. Observatios shared with Team | [12 empty] | Anoop
| VNS | EXTERNAL | GCCS-51222: Woked on Old Ticket with the team and observations shared with Client | [12 empty] | Anoop
| AHS | INTERNAL | Had Daily Stand Up Call | [12 empty] | Anoop/Arun

## 4th June
DEFECT
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
1 | Care Source | GCCS-53293 | HIGH | ISSUE | INC0908246 - Multiple Users experiencing issues with slowness, freezing, spinning | CLOSED | Shared the information with the client client confirmed and closed the ticket | Performance | N | N | 8.15.2022.02 | EST | PERFORMACE | N/A | PS | Arun

## 1st June (2)
DEFECT
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
| ICIRCLE | GCCS-51137 | LOW | ISSUE | Vision Claims have "Line" Info but no "Header" Info | IN CLIENT VALIDATION | INFORMATION has been shared with customer | INBOUND | N/A | N | 8.13.4.2022.02 | EST | INBOUND | N/A | INBOUND | Naresh
| HEALTH ALLIANCE | GCCS-51174 | HIGH | ISSUE | Auths not showing up to add to an appeal | IN PROGRESS | PS Team is working on this issue | CONFIG | N | N | 8.14.2022.03 | EST | UM | N/A | PS | Naresh
| UCARE | GCCS-51196 | CRITICAL | ISSUE | Dismissal letter does not have save/save & print buttons | IN CLIENT VALIDATION | Work around provided.Awaiting client response. | BROWSER CONFIG | Y | N | 8.10.2022.03 | EST | LETTERS | N/A | L2 team | Hari.C
| CARE SOURCE | GCCS-51188 | MEDIUM | ISSUE | Production: INC0906140 several users report still having empty queues | WAITING FOR CUSTOMER. | Requested client for additional information.Awaiting client response. | DATA ISSUE | N | Y | 8.16.2022.03 | EST | CM/UM | N/A | PS | Hari.C
| CARE SOURCE | GCCS-51166 | SEV1 | INCIDENT | Production: INC0906696 - multiple users reporting multiple GC issues starting near 10:45am | INVESTIGATING | Issue resolved.Awaiting RCA to be shared. | INFRASTRUCTURE | N/A | N | 8.16.2022.03 | EST | CM/UM | N/A | PS | Hari.C
| MED STAR | GCCS-51159 | LOW | ISSUE | Unable to Bulk Compete Required Activities | WAITING FOR CUSTOMER. | Requested client for additional information.Awaiting client response. | CODE FIX | N | Y | 8.15.2022.05 | EST | CM | N/A | PS | Hari.C
| CARE SOURCE | GCCS-51144 | MEDIUM | ISSUE | GC PROD; Remove Wrong Eligibility Span from Subscriber Record | WAITING FOR CUSTOMER. | Requested client for additional information.Awaiting client response. | DATA TASK | N/A | Y | 8.16.2022.03 | EST | UM | N/A | PS | Hari.C
| CARESOURCE | GCCS-51177 | MEDIUM | ISSUE | Production - no denial reasons for denial type outpatient administrative denial | CLOSED | Client confirmation received to close the ticket. | Training | N | N | 8.16.2022.03 | EST | UM | N/A | PS | Ambika
| CARESOURCE | GCCS-51156 | LOW | ISSUE | Member Eligibility is blank and causing issues | INVESTIGATING | Observation has been shared with L2 team. |  | Y | N | 8.16.2022.03 | EST | AG | N/A | L2 | Ambika
| CARESOURCE | GCCS-51190 | LOW | ISSUE | INC0873249- Issue with Script Attestations | INVESTIGATING | Validated the issue. |  | Y | N | 8.16.2022.03 | EST | CM | N/A | PS | Ambika
| MEDSTAR | GCCS-51147 | LOW | ISSUE | Required Activities | INVESTIGATING | PS team is working on this |  |  | N | 8.15.2022.05 | EST | CM | N/A | PS | Ambika
STORY
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
| UPHP | GCCS-51158 | MEDIUM | STORY | Update CM-Skilled to Custodial Referral/Communication Sheet Script Form | OPEN | Assigned to DM |  | N/A | N | 8.14.2022.02 | EST | CM | N/A | DM | Ambika
| CARESOURCE | GCCS-51151 | HIGH | STORY | 8.16 AG Resolution Details must be required fields | OPEN | Assigned to DM |  | N/A | N | 8.16.2022.03 | EST | AG | N/A | DM | Ambika
| MEDSTAR | GCCS-51186 | HIGH | STORY | DC 420 Report Duplicates | OPEN | Assigned to reports team for further action. | Reports | N/A | N | 8.15.2022.05 | EST | TABLEAU | N/A | REPORTS | Ambika
| EAST POINTE | GCCS-51212 | MEDIUM | STORY | Phase 4 - Housing Letter - Housing Application Withdrawal Letter | IN PROGRESS | Assigned to letters team | DATA CHANGES | N | N | 8.16.2022.02 | EST | CM | N/A | PS | Arun
TASK
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
| UCARE | GCCS-51189 | MEDIUM | TASK | Add Elena Hawj to daily file log email | IN PROGRESS | Inbound team is working on this request | INBOUND | N | N | 8.10.4.115 | EST | UM | N/A | INBOUND | Naresh
| PRIORITY HEALTH | GCCS-51183 | MEDIUM | TASK | Prod_ALT member ID inactive | IN PROGRESS | PS Team is working on this request | UPDATE REQUEST | N/A | N | 8.14.2022.03 | EST | CM/UM | N/A | PS | Naresh
1 | UPHP | GCCS-51149 | MEDIUM | TASK | DEI | IN PROGRESS | Assigned to Product BA | INBOUND | N/A | N/A | 8.14.2022.02 | EST | INBOUND | N/A | INBOUND | Naresh
1 | UPHP | GCCS-51148 | MEDIUM | TASK | Delete Consent | IN PROGRESS | PS Team is working on this request | UPDATE REQUEST | N/A | N/A | 8.14.2022.02 | EST | INBOUND | N/A | PS | Ajay
| PRIORITY HEALTH | GCCS-36654 | MEDIUM | TASK | Military Time Option for AG Module | IN PROGRESS | Assigned to Karen for further action | UPDATE REQUEST | N/A | N | 8.14.2022.03 | EST | CM/UM | N/A | Clinical SME | Naresh
| CALOPTIMA | GCCS-51192 | MEDIUM | TASK | Script is showing PENDING under CM module but is showing Completed under UM | INVESTIGATING | PS team working on this. | N/A | N/A | N | 8.13.4.2022.03 | PST | UM | N/A | PS | Hari.C
| ELDER PLAN | GCCS-51185 | MEDIUM | TASK | HEAT 273188 - Inquiry on Script Form Spell Check Option | CLOSED | Explanation Provided.Received client confirmation for closure. | ENQUIRY | N/A | N | 8.12.2022.05 | EST | CM | N/A | PS | Hari.C
| UCARE | GCCS-51150 | MEDIUM | TASK | Question on faxes and emails in Guiding Care v8.16 | CLOSED | Explanation Provided.Received client confirmation for closure. | ENQUIRY | N/A | N | 8.10.2022.03 | EST | CM | N/A | PS | Hari.C
| CARESOURCE | GCCS-51176 | MEDIUM | TASK | Letter Templates need to be push from SmartComm to QA1 UI | WAITING FOR CUSTOMER | Requested task has been completed. | Letters | N/A | N | 8.16.2022.03 | EST | CM | N/A | PS | Ambika
| EASTPOINTE | GCCS-51194 | MEDIUM | TASK | Production - User unable to login via SSO | INVESTIGATING | Assigned to Palukuri BalaKrishna | SSO | N/A | N | 8.16.2022.03 | EST | CM | N/A | PS | Ambika
| CALOPTIMA | GCCS-51191 | MEDIUM | TASK | Remove two Auths from Request Received widget that are grayed out | INVESTIGATING | Task will be performed post CCB approval. | Delete Request | N/A | N | 8.13.4.2022.02 | PST | UM | N/A | PS | Ambika
| HEALTH ALLIANCE | GCCS-26116 | MEDIUM | TASK | SSO for new users | INVESTIGATING | PS team is working on the request | SSO | N/A | N | 8.14.2022.03 | EST | CM | N/A | PS | Ambika
| ICIRCLE | GCCS-51170 | MEDIUM | TASK | Sync new activity: Transportation Escalation | INVESTIGATING | PS team is working on the sync request | SYNC REQUEST | N/A | N | 8.13.4.2022.02 | EST | CM | N/A | PS | Ambika
| MEDICA | GCCS-51161 | MEDIUM | TASK | Migrate New Letter to Production | INVESTIGATING | Task will be performed post CCB approval. | Letters | N/A | N | 8.15.2022.05 | EST | CM | N/A | PS | Ambika
| HEALTH ALLIANCE | GCCS-25960 | MEDIUM | TASK | Update the eligibility on an authorization | WAITING FOR CUSTOMER | Observation has been shared with the client. | Training | N/A | N | 8.14.2022.03 | EST | UM | N/A | PS | Ambika
| EASTPOINTE | GCCS-51187 | MEDIUM | TASK | Production - Delete Service Plans | INVESTIGATING | Task will be performed post CCB approval. | Delete Request | N/A | N | 8.16.2022.03 | EST | CM | N/A | PS | Ambika
| COA | GCCS-51213 | MEDIUM | TASK | Guiding Care Extract Process (QA) | IN PROGRESS | Assigned to development team | DATA CHANGES | N | N | 8.13.4.2022.01 | EST | EXTRACTS | N/A | PS | Arun
Ad-Hocs
SL.NO | Client | Internal/ External | Description
| CARE SOURCE | EXTERNAL | Worked on old ticket GCCS-33147# and shared update with the client. | [12 empty] | Hari.C
| EAST POINTE | EXTERNAL | Worked on old ticket GCCS-51119and shared update with the client. | [12 empty] | Hari.C
| AHS | INTERNAL | Had Daily Stand Up Call | [12 empty] | Ambika

## 2nd June (2)
DEFECT
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
| VNS | GCCS-51230 | Medium | Issue | Duplicate Email issue Geraldine Ferdinand | INVESTIGATING | PS Team is working on this | SSO | N/A | N | 8.16.2022.03 | EST | SSO |  | PS | Anoop
| MED STAR | GCCS-51232 | LOW | ISSUE | Program Activity: Program name not populating | INVESTIGATING | PS Team is working on this | CONFIG | N | Y | 8.15.2022.05 | EST | CM | N/A | PS | Naresh
| VNS | GCCS-51225 | Medium | Issue | Could not generate letter due to Errors | WAITING FOR CUSTOMER | Issue has been resolved.Awaiting client response. | Letter Movement | Y | N | 8.16.2022.05 | EST | LETTERS | N/A | PS | Hari.C/Ambika.S
| ELDERPLAN | GCCS-51235 | CRITICAL | ISSUE | HEAT 275538 - Healthcare Proxy Documents for Advanced Directives Are Not Uploading in Care Plan | WAITING FOR CUSTOMER | Waiting for client approval to perform the data correction. |  | Y | N | 8.12.2022.05 | EST | CM | N/A | PS | Ambika
| ELDER PLAN | GCCS-51248 | HIGH | ISSUE | HEAT 275612 - Mutual Members Did Not Generate in Service Authorization (Downstate) Script | IN PROGRESS | PS Team is working on this issue | CONFIG | N | N | 8.12.2022.01 | EST | CM | N/A | PS | Arun
| ELDER PLAN | GCCS-51253 | MEDIUM | ISSUE | Scroll bar not present when viewing script form via Form Layout - HEAT 275639 | IN PROGRESS | Shared the information with swat team | CONFIG | N | N | 8.12.2022.01 | EST | CM | N/A | SWAT INDIA | Arun
| EAST POINTE | GCCS-51233 | LOW | ISSUE | Production - Member Demographics - Date of Death/167549 | IN PROGRESS | Assigned to internal team | CONFIG | N | N | 8.16.2022.02 | EST | CM | N/A | PS | Arun
| ALOHACARE | GCCS-51256 | CRITICAL | ISSUE | Auth Packet does not include document attachments | INVESTIGATING | PS Team is working on this issue | ISSUE | N/A | N | 8.16.2022.03 | HST | UM | N/A | PS | Chandra
STORY
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
TASK
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
| PRIORITY HEALTH | GCCS-51229 | Medium | Task | Tableau - Staff Productivity report | OPEN | Assigned ro Reports Team | REPORTS | N/A | N | 8.14.2022.03 | EST | REPORTS |  | REPORTS | Anoop
| UCARE | GCCS-51223 | Medium | Task | Tableau access needed for the user | IN CLIENT VALIDATION | Waiting for Client Feedback | Access | N/A | N | 8.10.2022.02 | EST | CM |  | REPORTS | Anoop
1 | VNS | GCCS-51222 | Medium | Task | Configure T1028 code with IC and EX Modifiers | INVESTIGATING | Assigned to L2 team for further Task | Config | N/A | N | 8.16.2022.03 | EST | UM |  | L2 | Anoop
| ICIRCLE | GCCS-51241 | MEDIUM | TASK | Activity updates-Transportation Escalation, Transportation Reroute | INVESTIGATING | PS team is working on the sync request | SYNC REQUEST | N/A | N | 8.13.4.2022.02 | EST | CM | N/A | PS | Naresh
| DHMP | SDDHMP-2104 | CRITICAL | Task | Unable to access MCG | TECHNICAL ANALYSIS | Assigned to L2 team with observations for further analysis. | N/A | N | N | 8.11.0.M01 | MST | UM | N/A | L2 | Hari.C
| PRIORITY HEALTH | GCCS-51237 | MEDIUM | TASK | ODAG - Timestamp format | INVESTIGATING | Assigned to reports team for further action. | Reports | N/A | N | 8.14.2022.03 | EST | TABLEAU | N/A | REPORTS | Ambika
| ICIRCLE | GCCS-51242 | MEDIUM | TASK | Activity update: Submit for Withdrawal | INVESTIGATING | PS team is working on the sync request | SYNC REQUEST | N/A | N | 8.13.4.2022.02 | EST | CM | N/A | PS | Ambika
| ICIRCLE | GCCS-51247 | MEDIUM | TASK | New activity: Manual Enrollment Termination | INVESTIGATING | PS team is working on the sync request | SYNC REQUEST | N/A | N | 8.13.4.2022.02 | EST | CM | N/A | PS | Ambika
| MEDICA | GCCS-51246 | MEDIUM | TASK | Promote 6 New Letters to Production | WAITING FOR CUSTOMER | Requested for client approval. | Letters | N/A | N | 8.15.2022.05 | EST | AG | N/A | PS | Ambika
| x | GCCS-51252 | MEDIUM | TASK | Map service codes to IC and EX modifiers | IN PROGRESS | Shared the information with internal team | DATACHANGES | N | N | 8.12.2022.01 | EST | CM | N/A | PS | Arun
| UCARE | GCCS-51250 | MEDIUM | TASK | Tableau access - Lynn Price | IN PROGRESS | Assigned toTableau team | DATACHANGES | N | N | 8.10.4.115 | EST | TABLEAU | N/A | BI REPORTS | Arun
Ad-Hocs
SL.NO | Client | Internal/ External | Description
| AHS | INTERNAL | Had CCB Call
| AHS | INTERNAL | Had Daily Stand Up Call
| CALOPTIMA | INTERNAL | Worked on old ticket GCCS-51192 | [12 empty] | Hari.C/Bala.P
| UCARE | INTERNAL | Worked on old ticket GCCS-51196 and shared observations with L2 team. | [12 empty] | Hari.C
| MED STAR | INTERNAL | Worked on old ticket GCCS-51159 | [12 empty] | Hari.C
| MEDICA | INTERNAL | Worked on GCCS-22186 and details has been shared with the internal team. | [12 empty] | Ambika
| EASTPOINT | EXTERNAL | Worked on GCCS-51194 and requested client for more details. | [12 empty] | Ambika
| CARESOURCE | EXTERNAL | Worked on GCCS-51190 and observation has been shared with client. | [12 empty] | Ambika
| HAMP | EXTERNAL | Worked on GCCS-25960 and requested for the client approval to perform the task. | [12 empty] | Ambika
| VNS | EXTERNAL | Worked on GCCS-51225 and moved the changes from smartcomm side and the letter is working fine now. | [12 empty] | Ambika

## 6th June (2)
DEFECT
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
| UCARE | GCCS-55520 | CRITICAL | ISSUE | Missing 6/3 Loffler recon files | IN PROGRESS | Outbound team is working | OUTBOUND | N | N | 8.12.2022.01 | EST | CM | N/A | OUTBOUND | Naresh
| CARESOURCE | GCCS-55534 | LOW | ISSUE | Medical Claims we sent and don't see ever processed 6/3/2022 7:30:00 PM 6/4/2022 7:30:00 PM | INVESTIGATING | Assigned to Inbound team for further action. | INBOUND | N/A | N | 8.16.2022.03 | EST |  | N/A | INBOUND | Ambika
| CARESOURCE | GCCS-55552 | LOW | ISSUE | PROD: Service Plan Show Units Used in Auths | INVESTIGATING | PS team is working on this |  |  | N | 8.16.2022.03 | EST | UM | N/A | PS | Ambika
| PRIORITY HEALTH | GCCS-55539 | LOW | ISSUE | Member Portal - UAT - Script Performed Date and Script Competed Date data fields | INVESTIGATING | PS team is working on this |  |  | N | 8.14.2022.03 | EST | CM | N/A | PS | Ambika
| UCARE | GCCS-55562 | HIGH | ISSUE | Tableau Report ¦ Incorrect mapping | INVESTIGATING | Assigned to Inbound Team for further action | INBOUND | N/A | N | 8.12.2022.01 | EST | TABLEAU | N/A | INBOUND | Chandra
| CARE SOURCE | GCCS-55507 | Medium | Issue | Redeploy TAT configuration into QA1 and PP1 | INVESTIGATING | PS Team is working on this | Sync Task | N/A | N | 8.16.2022.03 | EST | AG | N/A | PS | Anoop
| UCARE | GCCS-55506 | High | Issue | UCare >> Production >> AG >> Member Complaint Log not populated | INVESTIGATING | Assigned to Implementation Team |  | Y | N | 8.16.2022.05 | EST | AG | N/A | Implementation | Anoop
| UCARE | GCCS-55508 | High | Issue | UCare >> Production >> AG >> Member Eligibility Linking issue | INVESTIGATING | Assigned to Implementation Team |  | Y | N | 8.16.2022.05 | EST | AG | N/A | Implementation | Anoop
| PRIORITY HEALTH | GCCS-55511 | CRITICAL | Issue | WQ file | WAITING FOR CUSTOMER | Observations shared with Client. Waiting for feedbcak | Data Loads | N/A | N | 8.14.2022.03 | EST | CM | N/A | Inbound | Anoop
STORY
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
| CARESOURCE | GCCS-55560 | HIGH | STORY | Risk of Admission Integration for OH Medicaid Go-Live | OPEN | Assigned to Sirisha Nadigadda | INBOUND | N/A | N | 8.16.2022.03 | EST |  | N/A | INBOUND | Ambika
TASK
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
| ICIRCLE | GCCS-55551 | Medium | Task | Enrollment reports data source update | Open | Assigned to Reports team to take it further | REPORTS | N/A | N | 8.13.4.2022.02 | EST | CM | N/A | REPORTS | Naresh
| CARESOURCE | GCCS-55532 | Medium | Task | Member address and phone updates - clarification | Open | Assigned to Inbound Team for further action | INBOUND | N/A | N | 8.16.2022.03 | EST | CM | N/A | INBOUND | Naresh
| VNS | GCCS-55509 | MEDIUM | TASK | Add 5 new CPT codes | IN PROGRESS | DB Team need to share the details | DATA CHANGES | N | N | 8.12.2022.01 | EST | CM | N/A | PS | Naresh
| UPHP | GCCS-55518 | MEDIUM | Task | Delete Consent | INVESTIGATING | Task will be performed post CCB approval. | Delete Request | N/A | N | 8.14.2022.02 | EST | CM | N/A | PS | Ambika
| CARESOURCE | GCCS-55525 | MEDIUM | Task | Developer Portal access - Saleem Davu | INVESTIGATING | Assigned to Bharani Mudumbai | Access Request | N/A | N | 8.16.2022.03 | EST | CM | N/A | IT | Ambika
| COA | GCCS-55538 | MEDIUM | Task | Bulk Merge Request - Jun. 6 | INVESTIGATING | Task will be performed post CCB approval. | Member Merge | N/A | N | 8.13.4.2022.01 | MST | CM | N/A | PS | Ambika
| ICIRCLE | GCCS-55553 | MEDIUM | TASK | Increase refresh frequency for Member Enrollment Trend month over month DS | INVESTIGATING | Assigned to reports team for further action. | Reports | N/A | N | 8.13.4.2022.02 | EST | TABLEAU | N/A | REPORTS | Ambika
| CARE SOURCE | GCCS-55521 | Medium | Task | Jira access request for Saleem Davu | Open | Asiigned to Interface Team | Access | N/A | N | 8.16.2022.03 | EST | Access Jra | N/A | Interface | Anoop
| Health Alliance | GCCS-55510 | Medium | Task | Jira Access | Open | Asiigned to Interface Team | Access | N/A | N | 8.14.2022.03 | EST | Access Jra | N/A | Interface | Anoop
| UCARE | GCCS-55523 | Medium | Task | 8.16 PROD: Message on Member's POC, "Eligibility has an issue" | INVESTIGATING | Assigned to Implementation Team |  | Y | N | 8.16.2022.05 | EST | CM | N/A | Implementation | Anoop
| UPHP | GCCS-55524 | High | Task | Member Portal Assessment Business Rule Update | OPEN | Assigned to Rules Team | Rules | N/A | N | 8.14.2022.02 | EST | CM | N/A | Rules | Anoop
Ad-Hocs
SL.NO | Client | Internal/ External | Description
1 | AHS | INTERNAL | Had Daily Stand Up Call | [12 empty] | Anoop/Arun/Ambika
2 | CARE SOURCE | GCCS-52960 | Shared the information with Swat team for further analysis | [12 empty] | Arun
3 | VNS | GCCS-24325 | Shared the information with the client waiting for client approval. | [12 empty] | Arun
4 | ELDER PLAN | GCCS-51120 | Shared the information with the client waiting for client feedback. | [12 empty] | Arun
5 | ELDER PLAN | GCCS-51248 | Shared the information with DB team for further analysis | [12 empty] | Arun
6 | COA | GCCS-52943 | Shared the information with the client waiting for client feedback. | [12 empty] | Arun
7 | MEDICA | GCCS-52950 | Shared the information with the client waiting for client feedback. | [12 empty] | Arun
8 | CARE SOURCE | GCCS-52961 | Shared the information with inbound team for further analysis | [12 empty] | Arun
9 | CARE SOURCE | GCCS-52962 | Shared the information with Outbound team for further analysis | [12 empty] | Arun
10 | PRIORITY HEALTH | GCCS-51121 | Shared the imeeting invitation with the client waiting for client feedback. | [12 empty] | Arun
11 | EAST POINTE | GCCS-51233 | Requesting L2 team to validate the issue as we have shared the HAR file to the team for furtehr analysis | [12 empty] | Arun
12 | PRIORITY HEALTH | GCCS-52953 | Shared the information with the client waiting for client feedback. | [12 empty] | Arun
13 | ALOHA CARE | GCCS-52959 | Shared the information with inbound team for further analysis | [12 empty] | Arun
14

## 7th June (2)
DEFECT
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
| UCARE | GCCS-55580 | MEDIUM | ISSUE | Unauthorized User - Linda Moua | INVESTIGATING | Assigned to Interface team | SSO | N/A | N | 8.16.2022.05 | EST | SSO | N/A | INTERFACE | Anoop
| CARE SOURCE | GCCS-55625 | Low | ISSUE | Guiding Care 8.16 - GUY as option opposed to GARS under RESP DEPT | INVESTIGATING | PS Team is working on this |  | N/A | N | 8.16.2022.03 | EST | AG | N/A | PS | Anoop
| CALOPTIMA | GCCS-55621 | MEDIUM | ISSUE | AHGC_DM_202205269999.txt not loaded into PreProd | INVESTIGATING | Assigned to Interface team | N/A | N/A | N | 8.13.4.2022.03 | PST | UM | N/A | PS | Naresh
| CARE SOURCE | GCCS-55673 | MEDIUM | ISSUE | PROD: Care Team Provider Reappears as Active After End Date Entered | INVESTIGATING | Assigned to Inbound Team | File Load | N/A | N | 8.16.2022.03 | EST | CM | N/A | PS | Hari.C
| PRIORITY HEALTH | GCCS-55637 | LOW | ISSUE | Medicare Appeals Complaints Report - No Data Refresh since 5/12 | INVESTIGATING | Assigned to reports team for further action. | Reports | N/A | N | 8.14.2022.03 | EST | TABLEAU | N/A | REPORTS | Ambika
| PRIORITY HEALTH | GCCS-55670 | Critical | ISSUE | Care Team reappearing in Guiding Care even when removed. | INVESTIGATING | Observation shared with Inbound team for further action. | INBOUND |  | N | 8.14.2022.03 | EST | INBOUND | N/A | INBOUND | Ambika
| HEALTH ALLIANCE | GCCS-55679 | High | ISSUE | Pharmacy claims load file errors | INVESTIGATING | Assigned to Inbound team for further action. | INBOUND | N/A | N | 8.14.2022.03 | EST | INBOUND | N/A | INBOUND | Ambika
| VNS | GCCS-55675 | MEDIUM | ISSUE | Question mark displaying in Auth notes | IN PROGRESS | PS Team is working on this issue | DATA CHANGES | N | N | 8.12.2022.01 | EST | CM | N/A | PS | Arun
STORY
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
| CARE SOURCE | GCCS-55677 | MEDIUM | STORY | UM User to User Mapping: Nightly mapping script update requested | IN PROGRESS | PS Team is working on this issue | DATA CHANGES | N | N | 8.16.2022.03 | EST | UM | N/A | PS | Arun
TASK
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
| MEDICA | GCCS-55617 | MEDIUM | TASK | Please remove this individual’s Tableau access, they are no longer with Medica, thanks. | Open | Assigned to Tableau Team | Tableau | N/A | N | 8.15.2022.05 | EST | CM | N/A | Tableau | Anoop
| EASTPOINTE | GCCS-55593 | MEDIUM | TASK | Production - Delete Service Plans - 189031 | INVESTIGATING | PS Team is working on this | DB | N/A | N | 8.16.2022.05 | EST | CM | N/A | PS | Anoop
| MEDICA | GCCS-55588 | MEDIUM | TASK | Please remove this individual’s Tableau access, they are no longer with Medica, thanks. | Closed | Client Validation received | Tableau | N/A | N | 8.15.2022.05 | EST | CM | N/A | Tableau | Anoop
| MEDICA | GCCS-55575 | MEDIUM | TASK | Process 278PA Magellan Files in QA Environment ¦ HR Upgrade testing | Open | Assigned to Inbound Team | Data Loads | N/A | N | 8.15.2022.05 | EST | CM | N/A | INBOUND | Anoop
| CARE SOURCE | GCCS-55590 | MEDIUM | TASK | Promote Letter Templates 2022_06_09 PP1 Defect Fix | Open | Assigned to L2 Team | Sync Task | N/A | N | 8.16.2022.03 | EST | Letters | N/A | L2 | Anoop
| MEDICA | GCCS-55599 | MEDIUM | TASK | AHS to load all Provider feeds as part of HR Payor 22.2 Upgrade into GC - PP | Open | Assigned to Inbound Team | Data Loads | N/A | N | 8.15.2022.05 | EST | CM | N/A | INBOUND | Anoop
| VNS | GCCS-55566 | HIGH | TASK | Move letter into QA instance for testing. | WAITING FOR CUSTOMER | Task Completed. Waiting for client feedback | Letter | N/A | N | 8.12.2022.01 | EST | CM | N/A | PS | Anoop
| CARE SOURCE | GCCS-55664 | MEDIUM | TASK | Requesting Altruista assistance with removing closed cases/activities from G&A work queues | INVESTIGATING | PS Team is working on this | DB | N/A | N | 8.16.2022.03 | EST | Letters | N/A | PS | Naresh
| MED STAR | GCCS-555579 | LOW | TASK | Requesting access to JIRA for Anoteros consultants | WAITING FOR CUSTOMER | Shared the information with client waiting for there response |  | N | N | 8.15.2022.03 | EST | AG | N/A | PS | Naresh
| CARESOURCE | GCCS-55634 | MEDIUM | Task | Manage Activity Mapping | INVESTIGATING | Assigned to Sripathi Aindleni | SYNC REQUEST | N/A | N | 8.16.2022.03 | EST | CM | N/A | L2 | Ambika
| CALOPTIMA | GCCS-55683 | MEDIUM | TASK | Auth with missing Eligibility please backend update | INVESTIGATING | Task will be performed post CCB approval. | UPDATE REQUEST | N/A | N | 8.13.4.2022.02 | PST | UM | N/A | PS | Ambika
Ad-Hocs
SL.NO | Client | Internal/ External | Description
1 | AHS | INTERNAL | Had Daily Stand Up Call | [12 empty] | Anoop/Arun/Ambika
2 | AHS | INTERNAL | Had CCB Call | [12 empty] | Anoop
3 | VNS | INTERNAL | GCCS-55507: Worked on the ticket and observations shared with Team | [12 empty] | Anoop
4 | CARE SOURCE | INTERNAL | GCCS-24256: Worked on the ticket and observations shared with Team | [12 empty] | Anoop
5 | ICIRCLE | INTERNAL | Worked on old ticket GCCS-51119 and observations shared with team | [12 empty] | Hari.C
6 | CALOPTIMA | INTERNAL | Worked on old ticket GCCS-14619 and observations shared with L2 team | [12 empty] | Hari.C
7 | CALOPTIMA | INTERNAL | Worked on old ticket GCCS-51192 and observations shared with L2 team | [12 empty] | Hari.C
8 | UCARE | INTERNAL | Internal discussion on GCCS-48986 | [12 empty] | Hari.C/Ajay/Bala.P
9 | HEALTH ALLIANCE | INTERNAL | Supported L2 team on GCCS-51128 | [12 empty] | Hari.C
10 | ICIRCLE | INTERNAL | Internal discussion on GCCS-16442 with ETL team | [12 empty] | Hari.C
11 | MED STAR | INTERNAL | Supported L2 team on GCCS-51159 | [12 empty] | Hari.C
12 | MEDICA | EXTERNAL | Worked on GCCS-5108 and requested task has been completed. | [12 empty] | Ambika
13 | MEDSTAR | INTERNAL | Worked on GCCS-51147 and observation has been shared with the L2 team. | [12 empty] | Ambika
| CARESOURCE | INTERNAL | Worked on GCCS-55552 and requested DB team to share the backend details. | [12 empty] | Ambika
| MEDICA | INTERNAL | Worked on GCCS-51246 and details has been shared with the internal team. | [12 empty] | Ambika
| COA | GCCS-52958 | Worked on old ticket and shared the information with the client | [12 empty] | Arun

## 8th June (2)
DEFECT
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
| CARESOURCE | GCCS-55713 | High | Issue | Provider Fax number incorrect in GC but shows correct in Facets | INVESTIGATING | Assigned to Inbound team for further investigation | Dataloads | Y | N | 8.16.2022.03 | EST | CM | N/A | Inbound | Anoop
| CARESOURCE | GCCS-55703 | Low | Issue | Promote 1 letter tagged with 2022_06_08 to PRD ASAP | INVESTIGATING | Assigned to L2 team | Sync | N/A | N | 8.16.2022.03 | EST | Letters | N/A | L2 | Anoop
| MEDICA | GCCS-55696 | High | Issue | There is an issue w/the Jira notifications | INVESTIGATING | Assigned to Interface team for further investigation | JIRA | N/A | N | 8.15.2022.05 | EST | Jira | N/A | Interface | Anoop
| CARESOURCE | GCCS-556 | Low | Issue | Please load CARESOURCE_AH_T_INCR_834_20220606064025.edi INCR to PP1 | INVESTIGATING | Assigned to Inbound team for further investigation | Dataloads | Y | N | 8.16.2022.03 | EST | Letters | N/A | PS | Naresh
| UCARE | GCCS-55741 | MEDIUM | ISSUE | Tableau Datasources ¦ Auth Status ¦ Missing information | INVESTIGATING | Assigned to REPORTS team for further investigation | REPORTS | N/A | N | 8.16.2022.05 | EST | TABLEAU | N/A | REPORTS | Chandra
STORY
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
TASK
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
| MEDSTAR | GCCS-55709 | Medium | Task | Need to move Authorization to a different member. | INVESTIGATING | PS Team is working on this | DB | N/A | N | 8.15.2022.05 | EST | UM | N/A | PS | Anoop
| ICIRCLE | GCCS-55704 | Medium | Task | Add SSN to Member Demography Secondary Pub data source | OPEN | Assigne to Reports Team | Reports | N/A | N | 8.13.4.2022.02 | EST | CM | N/A | Reports | Anoop
| CARESOURCE | GCCS-55712 | High | Task | UM Business Rule, Auto Assign to Work Queues After Intake Process Completed | OPEN | Assigne to Rules Team | Rules | N/A | N | 8.16.2022.03 | EST | CM | N/A | Rules | Anoop
| VNS | GCCS-55716 | Medium | Task | Inventory of All letters in GC | INVESTIGATING | PS Team is working on this | EXTRACT | N/A | N | 8.16.2022.03 | EST | Letters | N/A | PS | Hari.C
| ALTUS | SDALTUS-390 | High | Task | Access to Altus ACE JIRA Activity | WAITING FOR CUSTOMER | Requested for client for more detaila. |  | N/A | N | 8.8.0.66 | EST | JIRA | N/A | PS | Ambika
| ELDER PLAN | GCCS-55740 | MEDIUM | TASK | Issue: Users are unable to update Actual Discharge Date without having to change the date on the discharge page | IN PROGRESS | PS Team is working on this Task | DATA CHANGES | N | N | 8.12.2022.01 | EST | UM | N/A | PS | Arun
| MEDICA | GCCS-55732 | MEDIUM | TASK | Add Field Names Data Source | IN PROGRESS | Assigned to reports team | REPORTS | N | N | 8.15.2022.02 | EST | BI REPORTS | N/A | REPORTS | Arun
| PRIORITY HELTH | GCCS-55727 | MEDIUM | TASK | 8.17 Configuration Export Hidden | IN PROGRESS | PS Team is working on this Task | DATA CHANGES | N | N | 8.14.2022.03 | EST | CM | N/A | PS | Arun
Ad-Hocs
SL.NO | Client | Internal/ External | Description
1 | AHS | INTERNAL | Had Daily Stand Up Call | [12 empty] | Anoop/Arun/Ambika
| CARESOURCE | INTERNAL | GCCS-55625: Worked on old ticket. Observations shared with Team | [12 empty] | Anoop
| VNS | EXTERNAL | GCCS-24297: Worked on old ticket. Observations shared with Client | [12 empty] | Anoop
| PRIORITY HEALTH | EXTERNAL | GCCS-55670: Attended call with client | [12 empty] | Hari.C
| PRIORITY HEALTH | EXTERNAL | Attended PH weekly BAU call | [12 empty] | Hari.C
| CARESOURCE | INTERNAL | Worked on GCCS-51190 and observation has been shared with the L2 team. | [12 empty] | Ambika
| MEDICA | INTERNAL | Worked on old ticket and shared the information with Swat Team | [12 empty] | Arun
| CARE SOURCE | INTERNAL | Worked on old ticket and shared the information with Swat Team | [12 empty] | Arun
| COA | INTERNAL | Worked on old ticket and shared the information with PS DB Team | [12 empty] | Arun
| CARE SOURCE | INTERNAL | Worked on old ticket and shared the information with PS DB Team | [12 empty] | Arun
| VNS | INTERNAL | Worked on old ticket and shared the information with PS DB Team | [12 empty] | Arun

## 9th June
DEFECT
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
| CARESOURCE | GCCS-55750 | Low | Issue | Export from Worklog Manager Not Reflecting Data | INVESTIGATING | Observations shared with L2 team for further validation |  | Y | N | 8.16.2022.03 | EST | CM | N/A | L2 | Anoop
| CARESOURCE | GCCS-55748 | MEDIUM | Issue | MedicalClaims file received with no data for CSC_PROD_ErrorLog and CSC_PROD_Claims_FileLog | INVESTIGATING | Observations shared with Inbound team for further validation | INBOUND | Y | N | 8.16.2022.03 | EST | CM | N/A | INBOUND | Naresh
| MEDICA | GCCS-55760 | Low | Issue | INC1116830 complaint due date calculated incorrectly | CLOSED | Issue has been resolved from client side. | N/A | N | N | 8.15.2022.05 | EST | AG | N/A | PS | Hari.C
| MEDICA | GCCS-55765 | LOW | ISSUE | INC1116957 Member timeline missing from 5/27/2022 eligibility file | INVESTIGATING | Assigned to Inbound team for further action. | INBOUND | N/A | N | 8.15.2022.05 | EST | INBOUND | N/A | INBOUND | Ambika
| ELDERPLAN | GCCS-55788 | CRITICAL | ISSUE | HEAT 276484 - Documents Blocked When Users Attempt to Download | INVESTIGATING | PS team is working on this |  | Y | N | 8.12.2022.05 | EST | CM | N/A | PS | Ambika
STORY
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
TASK
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
| MEDICA | GCCS-55796 | MEDIUM | TASK | Script Form Change for Institutional Assessment | IN PROGRESS | Observatios are shared with L2 to take this request forward | FORMS | N | N | 8.15.2022.02 | EST |  | N/A | L2 | Naresh
| MEDICA | GCCS-55794 | MEDIUM | TASK | Script Form Change for CCP MSHO MSC Transfer HRA | IN PROGRESS | Observatios are shared with L2 to take this request forward | FORMS | N | N | 8.15.2022.02 | EST |  | N/A | L2 | Naresh
| CARESOURCE | GCCS-55755 | MEDIUM | TASK | Developer Portal Access | IN PROGRESS | Bharani is working to provide the access |  | N | N | 8.16.2022.03 | EST | CM | N/A | PS | Naresh
| PRIORITY HELTH | GCCS-55774 | MEDIUM | TASK | UAT_ADT test file load | IN PROGRESS | Observations shared with Inbound team for further validation | INBOUND | N | N | 8.14.2022.03 | EST | CM | N/A | INBOUND | Naresh
| UCARE | GCCS-55790 | MEDIUM | TASK | Tableau Datasource ¦ Ack Letter Sent date field | IN PROGRESS | Assigned to REPORTS team for further investigation | REPORTS | N/A | N | 8.16.2022.05 | EST | TABLEAU | N/A | REPORTS | Naresh
| MEDSTAR | GCCS-55793 | MEDIUM | TASK | Update Users' Access | IN PROGRESS | PS Team is working on this | CONFIG | N/A | N | 8.15.2022.05 | EST | UM | N/A | PS | Naresh
| CARESOURCE | GCCS-55782 | MEDIUM | Task | Please push letter templates from SmartComm to the UI | WAITING FOR CUSTOMER | Requested task has been completed. | Letters | N/A | N | 8.16.2022.03 | EST | CM | N/A | PS | Ambika
| MEDSTAR | GCCS-55764 | MEDIUM | Task | Historical Authorization file(s) for missing legacy data | INVESTIGATING | Assigned to Inbound team for further action. | INBOUND | N/A | N | 8.15.2022.05 | EST | INBOUND | N/A | INBOUND | Ambika
Ad-Hocs
SL.NO | Client | Internal/ External | Description
1 | AHS | INTERNAL | Had Daily Stand Up Call | [12 empty] | Anoop/Arun/Ambika
| AHS | INTERNAL | Had CCB Call | [12 empty] | Anoop
| Medica | External | GCCS-52721: Worked on Old ticket observations shared with Client | [12 empty] | Anoop
| EAST POINTE | INTERNAL | GCCS-51119: Discussion with F&A team on the ticket | [12 empty] | Hari.C
| UCARE | External | GCCS-48986: Validation and shared update with the client. | [12 empty] | Hari.C
| AHS | INTERNAL | Provided KT on PH module to internal team members | [12 empty] | Hari.C/Anoop/Ambika/Arun
| COA | EXTERNAL | Worked on old ticket GCCS-52958 and shared the information with the client | [12 empty] | Arun
| CARE SOURCE | INTERNAL | Worked on old ticket GCCS-52956 and shared the information with DB team | [12 empty] | Arun
| VNS | EXTERNAL | Worked on old ticket GCCS-52957 and shared the information with the client | [12 empty] | Arun
| VNS | INTERNAL | Worked on old ticket GCCS-55675 and shared the information with DB team | [12 empty] | Arun

## 10th June (2)
DEFECT
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
1 | CALOPTIMA | GCCS-55836 | MEDIUM | DEFECT | Script export not working | WAITING FOR CUSTOMER | Observation shared with client.Awaiting client response. | N/A | N | Y | 8.13.2.2022.05 | PST | CM | N/A | PS | Hari.C
2 | COA | GCCS-55849 | MEDIUM | DEFECT | Provider Search (Auto Populating Zip/Postal Code Field | WAITING FOR CUSTOMER | Observation shared with client.Awaiting client response. | TRAINING | N/A | N | 8.13.4.2022.01 | EST | CM | N/A | PS | Hari.C
| DHMP | GCCS-55825 | Critical | DEFECT | CM - Tableau Report Care Activity Summary missing Script | IN CLIENT VALIDATION | Observation shared with client.Awaiting client response. | Reports | N/A | N | 8.11.2022.04 | MST | CM | N/A | Reports | Anoop
| Health Alliance | GCCS-55834 | MEDIUM | DEFECT | Medicare Letters auto-generated | Investigating | Observations shared with Team for further Validation | Code | Y | N | 8.14.2022.03 | EST | CM | N/A | L2 | Anoop
| CARE SOURCE | GCCS-55814 | Medium | DEFECT | CSC_PROD_Claims_ErrorLog and CSC_PROD_Claims_FileLog not Received today | IN PROGRESS | Observatios are shared with Inbound to take this request forward | INBOUND | N/A | N | 8.16.2022.03 | EST | CM | N/A | INBOUND | Naresh
| HEALTH ALLIANCE | GCCS-55856 | High | ISSUE | NCQA monthly report pulling incorrect information | INVESTIGATING | Assigned to reports team for further action. | Reports | N/A | N | 8.14.2022.03 | EST | TABLEAU | N/A | REPORTS | Ambika
STORY
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
TASK
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
| CARE SOURCE | GCCS-55855 | Medium | Task | Prod: 278 resend 13 auths not in Facets, no 278 error we can find | Open | Assigned to Outbound Team | DataLoads | N/A | N | 8.16.2022.03 | EST | CM | N/A | OUTBOUND | Anoop
| MEDICA | GCCS-55822 | MEDIUM | TASK | AHS to load Gaps In Care File to GC PP as part of HR Payor Upgrade 22.2 | IN PROGRESS | Observatios are shared with Inbound to take this request forward | INBOUND | N | N | 8.15.2022.02 | EST |  | N/A | INBOUND | Naresh
| CARE SOURCE | GCCS-55816 | Medium | Task | OH MCD 7/1 - Prod: setup SSO to support login to GC with OH ID | IN PROGRESS | Observatios are shared with Ujwala to take this request forward | SSO | N/A | N | 8.16.2022.03 | EST | CM | N/A | PS | Naresh
| CARESOURCE | GCCS-55847 | MEDIUM | Task | Member Queue | INVESTIGATING | PS team is working on this |  | N/A | N | 8.16.2022.03 | EST | CM | N/A | PS | Ambika
| VNS | GCCS-55862 | Medium | Task | List of all letters in Production | INVESTIGATING | PS team is working on this request. | DB Report | N/A | N | 8.16.2022.05 | EST | CM | N/A | PS | Ambika
| PRIORITY HEALTH | GCCS-55863 | Medium | Task | Tableau Access | INVESTIGATING | Assigned to reports team for further action. | Reports | N/A | N | 8.14.2022.03 | EST | TABLEAU | N/A | REPORTS | Ambika
| VNS | GCCS-55860 | Medium | Task | Auths Not transferring to Facets | INVESTIGATING | Assigned to Outbound team for further action. | OUTBOUND | N/A | N | 8.16.2022.05 | EST | UM | N/A | OUTBOUND | Ambika
| VNS | GCCS-55865 | Medium | Task | Remove Appointment statuses | INVESTIGATING | PS team is working on this request. | Delete Request | N/A | N | 8.16.2022.05 | EST | CM | N/A | PS | Ambika
Ad-Hocs
SL.NO | Client | Internal/ External | Description
| CARE SOURCE | EXTERNAL | Attended client call on GCCS-51188 | [12 empty] | Hari.C
| ICIRCLE | INTERNAL | Worked on validation of ticket GCCS-24454 in Local instance | [12 empty] | Hari.C
| CARE SOURCE | EXTERNAL | Worked on old ticket GCCS-51144 and updated client for confirmation. | [12 empty] | Hari.C
| ICIRCLE | INTERNAL | Discussion on GCCS-51119 with F&A team member | [12 empty] | Hari.C
| AHS | INTERNAL | Had Daily Stand Up Call | [12 empty] | Anoop/Arun/Ambika

## 13th June (2)
DEFECT
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
1 | MedStar | GCCS-55898 | High | Issue | Guiding Care Production slowness | WAITING FOR CUSTOMER | Observations shared with Client. Waiting for their feedback | Performance | N/A | Y | 8.15.2022.05 | EST | CM | N/A | PS | Anoop
| MEDICA | GCCS-55887 | MEDIUM | Issue | Refresh Monitoring Report - Not working/Outdated | IN Triage | Observations shared with Reports team | REPORTS | N | N | 8.15.2022.02 | EST |  | N/A | REPORTS | Naresh
| PRIORITY HEALTH | GCCS-55869 | Medium | Issue | Unable to load fax error | INVESTIGATING | Obsrvations are shared with L2 |  | N/A | N | 8.14.2022.03 | EST | TABLEAU | N/A | L2 | Naresh
| ELDER PLAN | GCCS-55938 | High | Issue | Newly configured IAC No AC_Medicare Billable Denial Letter downloaded as PDF displays erroneous line | INVESTIGATING | Observations shared with L2 for further analysis. | LETTERS | Y | N | 8.12.2022.05 | EST | LETTERS | N/A | L2 | Hari.C
| PRIORITY HEALTH | GCCS-55941 | LOW | Issue | Staff unable to select multiple QA indicators within a readmission authorization | INVESTIGATING | PS team working on this. | N/A | N | N | 8.14.2022.03 | EST | UM | N/A | PS | Hari.C
| DHMP | GCCS-55921 | CRITICAL | ISSUE | SSO Error for GuidingCare QA | INVESTIGATING | Assigned to Ujwala Polepeddi. | SSO |  | N | 8.11.2022.04 | MST | CM | N/A | PS | Ambika
STORY
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
1 | MEDICA | GCCS-55919 |  | STORY | Extract - Publisher Data Sources Mapping and Definitions | OPEN | Assigned to Reports team | ENQUIRY | N/A | N | 8.15.2022.03 | EST | REPORTS | N/A | REPORTS | Hari.C
TASK
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
| CARESOURCE | GCCS-55934 | Medium | Task | Remove selected tables from replication | Open | Assigned to Madhav Rao | DB | N/A | N | 8.16.2022.03 | EST | CM | N/A | Interface | Anoop
| CARESOURCE | GCCS-55877 | Medium | Task | Tableau Access Request - Production | Closed | Access has been Provided | REPORTS | N/A | N | 8.16.2022.03 | EST | CM | N/A | REPORTS | Naresh
| CARESOURCE | GCCS-55874 | Medium | Task | Tableau Access Request - Production | Closed | Access has been Provided | REPORTS | N/A | N | 8.16.2022.03 | EST | CM | N/A | REPORTS | Naresh
| CARESOURCE | GCCS-55870 | Medium | Task | Tableau Access Request - Production | Closed | Access has been Provided | REPORTS | N/A | N | 8.16.2022.03 | EST | CM | N/A | REPORTS | Naresh
| MEDICA | GCCS-55950 | MEDIUM | TASK | Change automated user name for the HRP Auth file | INVESTIGATING | Assigned to Outbound team for further action. | OUTBOUND | N/A | N | 8.15.2022.05 | EST | OUTBOUND | N/A | OUTBOUND | Ambika
| CARESOURCE | GCCS-55937 | MEDIUM | TASK | JIRA Access | WAITING FOR CUSTOMER | Requested task has been completed. | Jira Access | N/A | N | 8.16.2022.03 | EST | JIRA | N/A | PS | Ambika
| ICIRCLE | GCCS-55952 | MEDIUM | TASK | Primary Care Provider Import Question | INVESTIGATING | PS team is working on this |  | N/A | N | 8.13.4.2022.02 | EST |  | N/A | PS | Ambika
Ad-Hocs
SL.NO | Client | Internal/ External | Description
| AHS | INTERNAL | Had Daily Stand Up Call | [12 empty] | Anoop/Ambika
| MEDICA | EXTERNAL | GCCS-33252: Worked on Old Ticket. Observations shared with Client | [12 empty] | Anoop
| CARESOURCE | INTERNAL | GCCS-55507: Worked on Old Ticket. Observations shared with Team | [12 empty] | Anoop
| UCARE | INTERNAL | GCCS-48986: Worked on old ticket | [12 empty] | Hari.C
| CARESOURCE | INTERNAL | Attended internal on GCCS-51188 with Inbound and L2 teams | [12 empty] | Hari.C
| MED STAR | INTERNAL | GCCS-51147: Internal discussion with L2 team on the ticket | [12 empty] | Hari.C
| CALOPTIMA | INTERNAL | GCCS-55836: Internal discussion with L2 team on the ticket
| COA | EXTERNAL | Worked on GCCS-55538 and observation has been shared with client. | [12 empty] | Ambika

## 14th June (2)
DEFECT
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
| CARESOURCE | GCCS-55980 | Critical | Issue | Issue with Risk in Other Privileges in the configuration store | INVESTIGATING | Observations shared with L2 team for further investigation |  | Y | N | 8.16.2022.03 | EST | CM | N/A | L2 | Anoop
| HEALTH ALLIANCE | GCCS-55979 | Critical | Issue | Missing load file for Signal provider partner | INVESTIGATING | Assigned to Inbound team | Data Loads | N/A | N | 8.14.2022.03 | EST | CM | N/A | Inbound | Anoop
| ICIRCLE | GCCS-55986 | MEDIUM | Issue | Error in PCSP form V1 | INVESTIGATING | PS team is working on this |  | N/A | N | 8.13.4.2022.02 | EST |  | N/A | PS | Naresh
| CARESOURCE | GCCS-56029 | MEDIUM | ISSUE | AG 8.16: Notification date/time disappears in GC | INVESTIGATING | PS team is working on this |  |  | N | 8.16.2022.03 | EST | AG | N/A | PS | Ambika
STORY
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
TASK
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
| ELDER PLAN | GCCS-55975 | Medium | TASK | HEAT 276761 - Request to Delete Outstanding Activities from Members' Records | WAITING FOR CUSTOMER | Waiting for client feedback | DB | N/A | N | 8.12.2022.05 | EST | CM | N/A | PS | Anoop
| VNS | GCCS-55996 | Medium | TASK | Urgent: Report needed - Pending Activities Inactive Work Queues | Open | PS Team is working on this | DB | N/A | N | 8.16.2022.05 | EST | CM | N/A | PS | Anoop
| DHMP | GCCS-56026 | MEDIUM | TASK | Manuel.Arevalo@dhha.org has not been able to access Tableau | Open | Assigned to reports team | Access | N/A | N | 8.11.0.M01 | MST | CM | N/A | REPORTS | Hari.C
| HEALTH ALLIANCE | GCCS-56006 | High | TASK | Change auth priority on authorization | INVESTIGATING | Task will be performed post CCB approval. | UPDATE REQUEST | N/A | N | 8.14.2022.03 | EST | UM | N/A | PS | Ambika
| CARESOURCE | GCCS-56018 | MEDIUM | TASK | Promote all letters tagged with 2022_06_18 Prod Deploy | INVESTIGATING | Assigned to Sripathi Aindleni. |  | N/A | N | 8.16.2022.03 | EST |  | N/A | L2 | Ambika
| DHMP | GCCS-56028 | MEDIUM | TASK | Shannon.Godbout@dhha.org has not been able to access Tableau | INVESTIGATING | Assigned to reports team for further action. | Reports | N/A | N | 8.11.2022.04 | MST | TABLEAU | N/A | REPORTS | Ambika
| MEDICA | GCCS-55985 | MEDIUM | TASK | Please sync new SmartComm template with GuidingCare | INVESTIGATING | Assigned to Palukuri BalaKrishna. | Letters | N/A | N | 8.15.2022.05 | EST | AG | N/A | PS | Ambika
| COA | GCCS-56025 | MEDIUM | TASK | Guiding Care Super User Account (Production, UAT, QA2) | WAITING FOR CUSTOMER | Observation has been shared with the client. |  | N/A | N | 8.13.4.2022.01 | MST | CM | N/A | PS | Ambika
| UCARE | GCCS-56039 | MEDIUM | TASK | Load new Acupuncture Referral Category Code | IN PROGRESS | Shared the information with inbound team | DATA CHANGES | N/A | N | 8.16.2022.05 | EST | UM | N/A | INBOUND | Arun
| UCARE | GCCS-56030 | MEDIUM | TASK | Tableau access - Molly McCaffrey | IN PROGRESS | Assigned to Teableau team | DATA CHANGES | N/A | N | 8.16.2022.05 | EST | REPORTS | N/A | TABLEAU | Arun
| MEDICA | GCCS-56113 | MEDIUM | TASK | Unable to successfully complete download from Manage Configurations | IN PROGRESS | PS team is working on this | DATA EXTRACT | N/A | N | 8.15.2022.05 | EST | CM | N/A | PS | Chandra
Ad-Hocs
SL.NO | Client | Internal/ External | Description
| AHS | INTERNAL | Had Daily Stand Up Call | [12 empty] | Arun/Anoop/Ambika
| AHS | INTERNAL | Had CCB Call | [12 empty] | Anoop
| VNS | INTERNAL | GCCS-24256: Worked on Old Ticket. Observations shared with Team | [12 empty] | Anoop
| HEALTH ALLIANCE | EXTERNAL | GCCS-25988: Worked on Old Ticket. Observations shared with Client | [12 empty] | Anoop
| UCARE | INTERNAL | GCCS-48986: Internal discussion on the ticket | [12 empty] | Hari.C/Bala.P/Ajay.K
| PRIORITY HEALTH | INTERNAL | GCCS-55941: Worked on the ticket and shared observations with L2 team | [12 empty] | Hari.C
| VNS | EXTERNAL | Worked on GCCS-55862 and details has been shared with the client. | [12 empty] | Ambika
| VNS | INTERNAL | Worked on old ticket GCCS-55675 and shared the information with L2 team | [12 empty] | Arun
| ELDERPLAN | INTERNAL | Worked on old ticket GCCS-51248 and shared the information with DB team | [12 empty] | Arun
| CARE SOURCE | INTERNAL | Worked on old ticket GCCS-52956 and shared the information with L2 Team | [12 empty] | Arun

## 15th June
DEFECT
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
| MEDICA | GCCS-56081 | MEDIUM | ISSUE | INC1119278 Failed HR authorizations in Guiding Care because of network outage | INVESTIGATING | Assigned to L2 team for further action. | API |  | N | 8.15.2022.05 | EST | UM | N/A | L2 | Ambika
STORY
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
TASK
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
| Care Source | GCCS-56061 | Medium | Task | Access to jira issue - page not fully loading to create ticekts | IN CLIENT VALIDATION | Task Completed | Access | N/A | N | 8.16.2022.03 | EST | CM | N/A | Interface | Anoop
| ElderPlan | GCCS-56054 | Medium | Task | Request for two new options within Request Sent field within Auth Basic Details accordion within UM Auth Template - HEAT 277047 | INVESTIGATING | PS Team is working on this | DB | N/A | N | 8.12.2022.05 | EST | CM | N/A | PS | Anoop
| Health Alliance | GCCS-56062 | Medium | Task | Adding new drug codes into GC | INVESTIGATING | PS Team is working on this | DB | N/A | N | 8.14.2022.03 | EST | CM | N/A | PS | Anoop
| MEDICA | GCCS-56080 | Medium | Task | New Folders For Fax Integration - Prior Authorization | OPEN | Assigned to L2 team to do the needful. | CONFIG | N/A | N | 8.15.2022.03 | EST | CM | N/A | L2 | Hari.C
| PRIORITY HEALTH | GCCS-56056 | Medium | Task | Update Jira Account Email | INVESTIGATING | Assigned to Bharani | Jira | N | N | 8.14.2022.03 | EST | UM | N/A | PS | Naresh
| ELDERPLAN | GCCS-56098 | MEDIUM | TASK | HEAT 276952 - Request to Add to the "Quick Update" Tab in Run Script Field for EP AN Role | INVESTIGATING | PS team is working on this request. |  | N/A | N | 8.12.2022.05 | EST | CM | N/A | PS | Ambika
| VNS | GCCS-56109 | MEDIUM | TASK | Health Indicator Report | INVESTIGATING | PS team is working on this request. | Data Extracts | N/A | N | 8.16.2022.05 | EST | CM | N/A | PS | Ambika
| CARESOURCE | GCCS-56074 | MEDIUM | TASK | Round 3 of Auto Ack Letters for FICO rule | INVESTIGATING | Assigned to Varahalu Babu Ganta Chitti. | FICO Rules | N/A | N | 8.16.2022.03 | EST | RULES | N/A | RULES | Ambika
| HEALTH ALLIANCE | GCCS-56107 | MEDIUM | TASK | InterQual Auto Auth and Business Rule Update | INVESTIGATING | Assigned to Varahalu Babu Ganta Chitti. | FICO Rules | N/A | N | 8.14.2022.03 | EST | RULES | N/A | RULES | Ambika
| ICIRCLE | GCCS-56082 | MEDIUM | TASK | New Script Added- Returned Mail Notification | INVESTIGATING | PS team is working on the sync request | SYNC REQUEST | N/A | N | 8.13.4.2022.02 | EST | CM | N/A | PS | Ambika
| UCARE | GCCS-56077 | MEDIUM | Task | Developer portal access - Manish Shakya | INVESTIGATING | Assigned to Bharani Mudumbai for further action. | Access Request | N/A | N | 8.16.2022.05 | EST | CM | N/A | IT | Ambika
| MEDSTAR | GCCS-56111 | MEDIUM | TASK | Request a new letter to closely mimic an existing letter | IN PROGRESS | Assigned to letters team | LETTERS | N/A | N | 8.15.2022.05 | EST | LETTER | N/A | LETTER | Arun
| MEDSTAR | GCCS-56112 | LOW | TASK | Letter will not populate address of provider and will not allow address to be manually updated. | IN PROGRESS | PS Team is working on this | LETTERS | N/A | N | 8.15.2022.05 | EST | LETTER | N/A | LETTER | Arun
Ad-Hocs
SL.NO | Client | Internal/ External | Description
| ElderPlan | Internal | GCCS-55975: Worked on Old Ticket . Observations shared with Team | [12 empty] | Anoop
| Health Alliance | External | GCCS-55996: Urgent: Report needed - Pending Activities Inactive Work Queues | [12 empty] | Anoop
| Care Source | Internal | GCCS-21471: Discussion with DB team on the request | [12 empty] | Hari.C
| PRIORITY HEALTH | External | Attended PH Weekly BAU call | [12 empty] | Hari.C
| CARESOURCE | EXTERNAL | Worked on GCCS-56029 and observation has been shared with client. | [12 empty] | Ambika
| MEDICA | EXTERNAL | Worked on GCCS-55985 and details has been shared with the client. | [12 empty] | Ambika
| VNS | INTERNAL | Worked on GCCS-55865 and details has been shared with the internal team. | [12 empty] | Ambika
| ELDERPLAN | INTERNAL | Worked on GCCS-55788 and observation has been shared with the L2 team. | [12 empty] | Ambika

## 16th June
DEFECT
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
1 | CARESOURCE | GCCS-56115 | MEDIUM | ISSUE | CM Documents are missing from GC | IN CLIENT VALIDATION | Update provided by inbound team.Awaiting client feedback. | FILE LOAD | N/A | N | 8.16.2022.03 | EST | CM | N/A | INBOUND | Hari.C
| CARESOURCE | GCCS-56074 | HIGH | ISSUE | TimeStamp for CRT environment is mismatching in Replication monitoring | WAITING FOR CUSTOMER | Observation has been shared with the client. | DBA | N/A | N | 8.16.2022.03 | EST |  | N/A | DBA | Ambika
STORY
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
TASK
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
| CARESOURCE | GCCS-56134 | MEDIUM | TASK | Tableau Access Request - Production | INVESTIGATING | Assigned to Kari for access | REPORTS | N/A | N | 8.16.2022.03 | EST | REPORTS | N/A | REPORTS | Naresh
| CARESOURCE | GCCS-56132 | MEDIUM | TASK | UM - Auth Priority Config Assistance: how to set up "true" tolling | INVESTIGATING | Assigned to Lavanya for Requirment analysis |  | N/A | N | 8.16.2022.03 | EST |  | N/A | BA | Naresh
| DHMP | GCCS-56156 | MEDIUM | TASK | Not all Merged members are appearing in member Merge search results | IN CLIENT VALIDATION | Explanation Provided.Awaiting client response. | CONFIG | N/A | N | 8.11.0.M01 | MST | CM | N/A | PS | Hari.C
| DHMP | GCCS-56152 | MEDIUM | TASK | Please Add / Update quarter 3 HCPC & CPT codes | OPEN | Assigned to Inbound team to do the needful. | FILE LOAD | N/A | N | 8.11.0.M01 | MST | UM | N/A | INBOUND | Hari.C
| DHMP | GCCS-56153 | MEDIUM | TASK | Please Add / Update quarter 3 HCPCS | OPEN | Assigned to Inbound team to do the needful. | FILE LOAD | N/A | N | 8.11.0.M01 | MST | UM | N/A | INBOUND | Hari.C
| DHMP | GCCS-56154 | MEDIUM | TASK | Please Update quarter 3 HCPCS | OPEN | Assigned to Inbound team to do the needful. | FILE LOAD | N/A | N | 8.11.0.M01 | MST | UM | N/A | INBOUND | Hari.C
| UCARE | GCCS-56157 | MEDIUM | TASK | Tableau ¦ Authorizations data source ¦ Incomplete results | OPEN | Assigned to reports team for analysis. | REPORTS | N/A | N | 8.16.2022.03 | EST | REPORTS | N/A | REPORTS | Hari.C
| ICIRCLE | GCCS-56151 | MEDIUM | TASK | Default activity time-30 minutes | IN CLIENT VALIDATION | Explanation Provided.Awaiting client response. | ENQUIRY | N/A | N | 8.13.4.2022.05 | EST | CM | N/A | PS | Hari.C
| MEDICA | GCCS-56117 | MEDIUM | TASK | Import Level Mappings in QA for Keystone Project Products | OPEN | PS team working on the request | CONFIG SYNC | N/A | N | 8.15.2022.06 | EST | CM | N/A | PS | Hari.C
| ICIRCLE | GCCS-56143 | MEDIUM | TASK | New activity added: Send Transportation Authorization | INVESTIGATING | PS team is working on the sync request | SYNC REQUEST | N/A | N | 8.13.4.2022.02 | EST | CM | N/A | PS | Ambika
| ICIRCLE | GCCS-56148 | MEDIUM | TASK | New activity-Review Involuntary Disenrollment package | INVESTIGATING | PS team is working on the sync request | SYNC REQUEST | N/A | N | 8.13.4.2022.02 | EST | CM | N/A | PS | Ambika
| ICIRCLE | GCCS-56150 | MEDIUM | TASK | Sync new document types to UAT: NYIA forms | INVESTIGATING | PS team is working on the sync request | SYNC REQUEST | N/A | N | 8.13.4.2022.02 | EST | CM | N/A | PS | Ambika
| ICIRCLE | GCCS-56146 | MEDIUM | TASK | Request to sync updated script: IDT Meeting | INVESTIGATING | PS team is working on the sync request | SYNC REQUEST | N/A | N | 8.13.4.2022.02 | EST | CM | N/A | PS | Ambika
| CARESOURCE | GCCS-56140 | MEDIUM | TASK | Please push letter templates from SmartComm to the UI | WAITING FOR CUSTOMER | Requested task has been completed. | Letters | N/A | N | 8.16.2022.03 | EST | LETTER | N/A | PS | Ambika
| ICIRCLE | GCCS-56147 | MEDIUM | TASK | Please add PR (Puerto Rico) as a state in the Member Details | INVESTIGATING | PS team is working on the request |  | N/A | N | 8.13.4.2022.02 | EST | CM | N/A | PS | Ambika
| CARESOURCE | GCCS-56145 | MEDIUM | TASK | Need data element tied to field pushed to AG Module | INVESTIGATING | Assigned to Ravindra Anaparthi for further action. | Letters | N/A | N | 8.16.2022.03 | EST | LETTER | N/A | LETTERS | Ambika
| DHMP | GCCS-56144 | MEDIUM | TASK | Carrier ID Default | INVESTIGATING | PS team is working on this |  | N/A | N | 8.11.2022.04 | MST | CM | N/A | PS | Ambika
| MEDICA | GCCS-56178 | LOW | TASK | INC1119733 can't get into preprod guiding care | IN PROGRESS | Assigned to Zach for further assistance | SSO | N/A | N | 8.15.2022.02 | EST | SSO | N/A | SSO | Arun
| UCARE | GCCS-56161 | MEDIUM | TASK | Tableau ¦ Decisions data source ¦ Missing Field | IN PROGRESS | Assigned to reports team for analysis. | REPORTS | N/A | N | 8.16.2022.03 | EST | REPORTS | N/A | REPORTS | Arun
| HEALTH ALLIANCE | GCCS-56159 | MEDIUM | TASK | SSO for new user | IN PROGRESS | Assigned to DB team for analysis. | SSO | N/A | N | 8.14.2022.03 | EST | SSO | N/A | SSO | Arun
| ALOHACARE | GCCS-56179 | MEDIUM | TASK | Update auth priority for auth 0616TWYEJ | INVESTIGATING | PS team is working on the request | UPDATE REQUEST | N/A | N | 8.14.2022.03 | HST | CM | N/A | PS | Chandra
| MED STAR | GCCS-56158 | MEDIUM | TASK | QA Access for New Users | IN PROGRESS | Need more inputs from the client | ACCESS | N/A | N | 8.15.2022.05 | EST | CM | N/A | PS | Arun
| ICIRCLE | GCCS-56155 | MEDIUM | TASK | Number of pending requests discrepancies between Worklog Mgr, Pending activities and Requests received | IN PROGRESS | PS Team is working on this ticket | PERFORMANCE | N/A | N | 8.13.4.50 | EST | CM | N/A | PS | Arun
Ad-Hocs
SL.NO | Client | Internal/ External | Description
1 | PRIORITY HEALTH | INTERNAL | Supported L2 team member on the ticket GCCS-55869 | [12 empty] | Hari.C
2 | CARESOURCE | INTERNAL | supported L2 team member on the ticket GCCS-52956 | [12 empty] | Hari.C
| ALTRUISTA | INTERNAL | Had a call with CCB regarding iTop tickets. | [12 empty] | Ambika
| MEDICA | INTERNAL | Worked on GCCS-55985 and details has been shared with the internal team. | [12 empty] | Ambika
| ELDERPLAN | EXTERNAL | Worked on GCCS-56098 and observation has been shared with client. | [12 empty] | Ambika

## 17th June
DEFECT
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
1 | UCARE | GCCS-56219 | MEDIUM | ISSUE | Tableau ¦ Activity Creation Report Data Source ¦ Unexpected Results | OPEN | Assigned to Reports for analysis | Reports | N/A | N | 8.16.2022.05 | EST | REPORTS | N/A | REPORTS | Hari.C
2 | COA | GCCS-56218 | MEDIUM | ISSUE | Decision Status/Status Code Drop Down (Missing Options) | CLOSED | Explanation Provided.Awaiting client response. | CONFIGURATION | N/A | N | 8.13.4.2022.01 | EST | UM | N/A | PS | Hari.C
| CARE SOURCE | GCCS-56187 | LOW | ISSUE | INC0885374- member has a duplicated Aid Supplemental Value | INVESTIGATING | Team is working for resolution |  | N/A | N | 8.16.2022.03 | EST | CM | N/A | PS | Naresh
| ICIRCLE | GCCS-56209 | MEDIUM | ISSUE | One User Unable to sign into Production | CLOSED | Issue has been resolved | SSO | N/A | N | 8.13.4.2022.02 | EST | CM | N/A | PS | Naresh
1 | UCARE | GCCS-56228 | MEDIUM | ISSUE | Tableau Report ¦ Change Owner | INVESTIGATING | Assigned to Reports for analysis | Reports | N/A | N | 8.16.2022.05 | EST | REPORTS | N/A | REPORTS | Naresh
| CALOPTIMA | GCCS-56236 | HIGH | ISSUE | When searching Complaint from Member search wrong Complaint ID are showing | INVESTIGATING | Shared the information with Swat team | CONFIG | Y | N | 8.13.2.2022.05 | PST | A&G | N/A | SWAT-INDIA | Arun
| CARE SOURCE | GCCS-56232 | LOW | ISSUE | INC0913930: Letter Generation Authentication | INVESTIGATING | PS Team is working on this issue | LETTER | N/A | N | 8.16.2022.03 | EST | LETTER | N/A | PS | Arun
STORY
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
| EASTPOINTE | GCCS-56199 | MEDIUM | STORY | Tailored Plan - Non-Discrimination Letter - Update | INVESTIGATING | Assigned to Ganesh for review | LETTERS | N/A | N | 8.16.2022.05 | EST | CM | N/A | LETTERS | Naresh
| EASTPOINTE | GCCS-56201 | MEDIUM | STORY | Tailored Plan - Non-Discrimination Letter_SP - Update | INVESTIGATING | Assigned to Ganesh for review | LETTERS | N/A | N | 8.16.2022.05 | EST | CM | N/A | LETTERS | Naresh
| MEDICA | GCCS-56214 | MEDIUM | STORY | Letter Template ID Suffix Requirement | INVESTIGATING | Assigned to letters team | LETTER | N/A | N | 8.15.2022.02 | EST | LETTER | N/A | LETTER | Arun
TASK
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
| CARE SOURCE | GCCS-56204 | MEDIUM | TASK | Add user to Guiding Care File Alert DL | INVESTIGATING | Assigned to Inbound team to do the needful | ENQUIRY | N/A | N | 8.16.2022.03 | EST | CM | N/A | INBOUND | Hari.C
| COA | GCCS-56197 | MEDIUM | TASK | Duplicate Email ID ( UAT and Production) | OPEN | PS team working on the request | DATA TASK | N/A | N | 8.13.4.2022.01 | EST | CM | N/A | PS | Hari.C
| DHMP | GCCS-56196 | MEDIUM | TASK | Holly.Dinh@dhha.org has not been able to access Tableau | OPEN | Assigned to reports team for analysis | ACCESS | N/A | N | 8.11.0.M01 | MST | REPORTS | N/A | REPORTS | Hari.C
| UPHP | GCCS-56193 | MEDIUM | TASK | Nesting fields in a script form | INVESTIGATING | Assigned to L2 team with observations for further analysis | ENQUIRY | N/A | N | 8.14.2022.02 | EST | CM | N/A | L2 | Hari.C
| MED STAR | GCCS-56188 | MEDIUM | TASK | Message lines that display in the Smartcom Letter tool under preview letter | INVESTIGATING | Assigned to L2 team with observations for further analysis | LETTERS | Y | N | 8.15.2022.05 | EST | LETTERS | N/A | L2 | Hari.C
| COA | GCCS-56223 | MEDIUM | TASK | Provider File Load to Production | OPEN | Assigned to Inbound team to do the needful | FILE LOAD | N/A | N | 8.13.4.2022.01 | EST | INBOUND | N/A | INBOUND | Hari.C
| VNS | GCCS-56211 | MEDIUM | TASK | Activity report and completion from backend | INVESTIGATING | PS team is working on this request. | Data Extracts | N/A | N | 8.16.2022.05 | EST | CM | N/A | PS | Naresh
| HEALTH ALLIANCE | GCCS-56202 | MEDIUM | TASK | SSO access for new user | IN PROGRESS | Assigned to DB team for analysis. | SSO | N/A | N | 8.14.2022.03 | EST | SSO | N/A | PS | Naresh
| UCARE | GCCS-56235 | LOW | TASK | Tableau ¦ Decisions Data source ¦ Missing information | INVESTIGATING | Assigned to reports team | REPORTS | N/A | N | 8.16.2022.03 | EST | REPORTS | N/A | REPORTS | Arun
| VNS | GCCS-56231 | MEDIUM | TASK | Report of all auths with 5 digit Req/Apr amount | INVESTIGATING | Assigned to Outbound team for further analysis | OUTBOUND | N/A | N | 8.12.2022.01 | EST | OUTBOUND | N/A | OUTBOUND | Arun
| CARE SOURCE | GCCS-56212 | MEDIUM | TASK | API user has a gmail address associated, need review to validate no email out | Need Client Input | Need more clarity on the issue | API | N/A | N | 8.16.2022.03 | EST | API | N/A | PS | Arun
Ad-Hocs
SL.NO | Client | Internal/ External | Description
| ICIRCLE | EXTERNAL | Worked on old ticket GCCS-56151 and shared update with the client. | [12 empty] | Hari.C

## 21th June (2)
DEFECT
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
1 | CARE SOURCE | GCCS-56320 | LOW | ISSUE | 8.16 AG Guiding Care Claim Search Filter Not Working Correctly | INVESTIGATING | Observations shared with L2 team for further analysis. | CODE FIX | Y | N | 8.16.2022.05 | EST | A&G | N/A | L2 | Hari.C
| UCARE | GCCS-56313 | LOW | ISSUE | Provider selection under Intake Details | WAITING FOR CUSTOMER | Explanation provided.Awaiting client response. | TRAINING | N/A | N | 8.16.2022.05 | EST | A&G | N/A | PS | Hari.C
| ELDER PLAN | GCCS-56310 | CRITICAL | ISSUE | Missing data when generating the Staff Attendance Report from Tableau - HEAT 277578 | INVESTIGATING | Assigned to Reports team for analysis. | REPORTS | N/A | N | 8.12.2022.05 | EST | REPORTS | N/A | REPORTS | Hari.C
| MEDICA | GCCS-56279 | MEDIUM | ISSUE | GC Patch upgrade testing ¦ COSMOS preprod OCH Auth - 50105015 missed to extract - 20/06/2022 | WAITING FOR CUSTOMER | Observation has been shared with the client. | OUTBOUND | N/A | N | 8.15.2022.06 | EST | UM | N/A | OUTBOUND | Ambika
| MEDICA | GCCS-56251 | HIGH | ISSUE | Issue on triggered letters from GC Preprod are not sent to MFT folders | WAITING FOR CUSTOMER | Observation has been shared with the client. | OUTBOUND | N/A | N | 8.15.2022.06 | EST | UM | N/A | OUTBOUND | Ambika
| CARESOURCE | GCCS-56283 | CRITICAL | ISSUE | CM Documents are missing from GC from 6/20/2022 | INVESTIGATING | Assigned to Inbound team for further action. | INBOUND | N/A | N | 8.16.2022.03 | EST | INBOUND | N/A | INBOUND | Ambika
| VNS | GCCS-56258 | CRITICAL | ISSUE | Duplicate Alternate Service ID | WAITING FOR CUSTOMER | Observation has been shared with the client. |  | Y | Y | 8.16.2022.05 | EST | UM | N/A | PS | Ambika
| UPHP | GCCS-56318 | LOW | ISSUE | Poogram wont close | INVESTIGATING | PS team is working on this. |  |  | N | 8.14.2022.02 | EST | CM | N/A | PS | Ambika
| UCARE | GCCS-56301 | MEDIUM | ISSUE | JIRA access - Glenn Burgstahler | INVESTIGATING | Assigned to Bharani Mudumbai | Jira | N/A | N | 8.16.2022.05 | EST | JIRA | N/A | IT | Ambika
| CARE SOURCE | GCCS-56245 | HIGH | ISSUE | Defect - Duplicated Script OHCW EBU Assessment v2 Introduced to Production on Sync | INVESTIGATING | Observations shared with L2 team for further analysis. | DATA TASK | Y | N | 8.16.2022.05 | EST | CM | N/A | L2 | Hari.C
| VNS | GCCS-56274 | MEDIUM | ISSUE | Auth # 0609T968C unable to close | WAITING FOR CUSTOMER | Explanation provided.Awaiting client response. | DATA TASK | Y | N | 8.16.2022.05 | EST | UM | N/A | PS | Hari.C
| MEDICA | GCCS-56329 | LOW | ISSUE | INC1121260 letter was not received timely by Medica | IN PROGRESS | PS Team is working on this issue | LETTERS | N | N | 8.15.2022.02 | EST | LETTERS | N/A | LETTERS | Arun
STORY
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
TASK
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
1 | HEALTH ALLIANCE | GCCS-56322 | MEDIUM | TASK | SSO for new users | OPEN | PS team working on the request | SSO | N/A | N | 8.14.2022.03 | EST | CM | N/A | PS | Hari.C
2 | ELDER PLAN | GCCS-56295 | MEDIUM | TASK | Request report of all Scripts and Script Forms currently in Pending status - HEAT 277506 | CLOSED | Requested extract has been shared.Received client confirmation for closure. | EXTRACT | N/A | N | 8.12.2022.05 | EST | CM | N/A | PS | Hari.C/Bala.P
3 | MEDICA | GCCS-56307 | MEDIUM | TASK | Letter Layout Capabilities | OPEN | Assigned to Letters team for analysis. | ENQUIRY | N/A | N | 8.15.2022.05 | EST | LETTERS | N/A | LETTERS | Hari.C
| ELDERPLAN | GCCS-56289 | MEDIUM | TASK | Request for Excel list of all All CM and UM letters In Production | CLOSED | Client confirmation received to close the ticket. | Data Extracts | N/A | N | 8.12.2022.05 | EST | CM | N/A | PS | Ambika
| ICIRCLE | GCCS-56282 | MEDIUM | TASK | Add "Hours" to UM data Source | INVESTIGATING | Assigned to reports team for further action. | Reports | N/A | N | 8.13.4.2022.02 | EST | TABLEAU | N/A | REPORTS | Ambika
| UCARE | GCCS-56304 | MEDIUM | TASK | GuidingCare developer portal access - Sean Nagel | INVESTIGATING | Assigned to Bharani Mudumbai. | Access Request | N/A | N | 8.16.2022.05 | EST | CM | N/A | IT | Ambika
| UCARE | GCCS-56303 | MEDIUM | TASK | Tableau access - Camila Souza | IN CLIENT VALIDATION | Requested task has been completed. | Reports | N/A | N | 8.16.2022.05 | EST | TABLEAU | N/A | REPORTS | Ambika
| UCARE | GCCS-56323 | MEDIUM | TASK | Tableau access - Laura Church | IN CLIENT VALIDATION | Requested task has been completed. | Reports | N/A | N | 8.16.2022.05 | EST | TABLEAU | N/A | REPORTS | Ambika
| EASTPOINTE | GCCS-56284 | MEDIUM | TASK | Production - Delete Clinical Program - Member 453362 | INVESTIGATING | Task will be performed post CCB approval. | Delete Request | N/A | N | 8.16.2022.03 | EST | CM | N/A | PS | Ambika
| COA | GCCS-56314 | MEDIUM | TASK | New Auth extract to only include Supplier Location | INVESTIGATING | PS team is working on this request. |  | N/A | N | 8.13.4.2022.01 | MST | CM | N/A | PS | Ambika
| UCARE | GCCS-56302 | MEDIUM | TASK | Add Rachel Whitcomb to daily file log email | INVESTIGATING | Assigned to Inbound team for further action. | INBOUND | N/A | N | 8.16.2022.05 | EST | INBOUND | N/A | INBOUND | Ambika
| CARESOURCE | GCCS-56296 | MEDIUM | TASK | Need update to N Level Plan name for Akron Children's | INVESTIGATING | Assigned to Sripathi Aindleni. |  | N/A | N | 8.16.2022.03 | EST | CM | N/A | L2 | Ambika
| HEALTH ALLIANCE | GCCS-56332 | MEDIUM | TASk | SSO access for new user | IN PROGRESS | Assigned to DB team for analysis. | SSO | Y | N | 8.14.2022.03 | EST | SSO | N/A | SSO | Arun
| DHMP | GCCS-56330 | MEDIUM | TASK | Tableau Access - Robin Bun | IN PROGRESS | Assigned to Tableau team | Reports | N | N | 8.11.0.M01 | MST | REPORTS | N/A | REPORTS | Arun
Ad-Hocs
SL.NO | Client | Internal/ External | Description
1 | MEDICA | EXTERNAL | Worked on old ticket GCCS-55950# and updated to client. | [12 empty] | Hari.C
| ALTRUISTA | INTERNAL | Had a call with CCB regarding iTop tickets. | [12 empty] | Ambika
| MEDICA | EXTERNAL | Worked on GCCS-55985 and requested task has been completed. | [12 empty] | Ambika
| CARE SOURCE | EXTERNAL | Worked on old ticket GCCS-56232 and shared the information with the client | [12 empty] | Arun
| VNS | INTERNAL | Worked on old ticket GCCS-56231 and shared the information with internal team | [12 empty] | Arun
| CARE SOURCE | INTERNAL | Worked on old ticket GCCS-56212 and shared the information with internal team | [12 empty] | Arun
| ICIRCLE | INTERNAL | Worked on old ticket GCCS-56155 and shared the information with internal team | [12 empty] | Arun
| MED STAR | INTERNAL | Worked on old ticket GCCS-56158 and shared the information with internal team | [12 empty] | Arun
| MED STAR | INTERNAL | Worked on old ticket GCCS-56112 and shared the information with internal team | [12 empty] | Arun

## 22nd June (2)
DEFECT
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
1 | HEALTH ALLIANCE | GCCS-56629 | Low | Issue | Jira Access Issue | WAITING FOR CUSTOMER | Issue resolved. Wating for validation | User Access | N/A | N | 8.14.2022.03 | EST | JIRA | N/A | Interface | Anoop
| MedStar | GCCS-56597 | Low | Issue | USER TANYA SETTLERS unable to Access ALTRUISTA via SSO | INVESTIGATING | PS Team is working on this | SSO | N/A | N |  | EST | SSO | N/A | PS | Anoop
| Care Source | GCCS-56527 | Medium | Issue | PUT /Complaint unable to update record due to workQueues[0].careStaffUserName[1] error | INVESTIGATING | Observations shared with L2 Team | DB | N/A | N |  | EST | AG | N/A | L2 | Anoop
| Medica | GCCS-56613 | Low | Issue | INC1121548 getting "unauthorized user" when SSO into Guiding Care Production | INVESTIGATING | PS Team is working on this | SSO | N/A | N |  | EST | SSO | N/A | PS | Anoop
| MEDICA | GCCS-56650 | LOW | ISSUE | INC1117375 Unable to close the Transplant Program in Guiding Care | INVESTIGATING | PS team is working on this. |  | Y | N | 8.15.2022.06 | EST | CM | N/A | PS | Ambika
| MED STAR | GCCS-56654 | MEDIUM | ISSUE | Date of Service not populating on Complaint Summary | IN PROGRESS | PS Team is working on this issue | CONFIG | N/A | N | 8.15.2022.05 | EST | AG | N/A | PS | Arun
STORY
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
| MEDICA | GCCS-56632 | HIGH | STORY | Add New Field to Publisher Data sources in Prod and Preprod environments | Open | Assigned to Reports Team for further analysis | CR | N/A | N | 8.15.2022.05 | EST | REPORTS | N/A | Reports | Hari.C
| EASTPOINTE | GCCS-56635 | MEDIUM | STORY | Tailored Plan - Letter Updates Needed to Meet State Requirements | OPEN | Assigned to Vijaisarathi Duggaraju | CR | N/A | N | 8.16.2022.03 | EST | CM | N/A | LETTERS | Ambika
TASK
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
1 | PRIORITY HEALTH | GCCS-56031 | Medium | Task | CMH/PIHP Care Coordination Program | INVESTIGATING | Observations shared with L2 Team | DB | N/A | N |  | EST | CM | N/A | L2 | Anoop
2 | Care Source | GCCS-56596 | Medium | Task | PP1 Deploy Requested for 06222022 | Open | Assigned to L2 team for the Sync request | Sync Request | N/A | N |  | EST | CM | N/A | L2 | Anoop
3 | ICircle | GCCS-56525 | Medium | Task | New document types added for NYIA | INVESTIGATING | PS Team is working on this | Sync Request | N/A | N |  | EST | CM | N/A | PS | Anoop
| ICircle | GCCS-56600 | Medium | Task | UM Decision TAT Data Source Missing some historical Auths | Open | Assigned to Reports Team for further task |  | N/A | N |  | EST | UM |  | Reports | Anoop
| PRIORITY HEALTH | GCCS-56631 | Medium | Task | WQ File | CLOSED | Requested load has been completed by Inbound team.Received client feedback for closure. | FILE LOAD | N/A | N | 8.14.2022.03 | EST | CM | N/A | Interface | Hari.C
| VNS | GCCS-56604 | MEDIUM | TASK | Person Centered Service Plan sending to Command | INVESTIGATING | Assigned to outbound team for further action. | OUTBOUND | N/A | N | 8.16.2022.05 | EST | CM | N/A | OUTBOUND | Ambika
| HEALTH ALLIANCE | GCCS-56649 | MEDIUM | TASK | New drug codes to be added into GC | INVESTIGATING | PS team is working on this request. |  | N/A | N | 8.14.2022.03 | EST | UM | N/A | PS | Ambika
Ad-Hocs
SL.NO | Client | Internal/ External | Description
1 | AHS | Internal | GCCS-56526: ad Internal discussion wrt the issue | [12 empty] | Anoop
2 | Medica | EXTERNAL | GCCS-51246: Worked on the old ticket. Client validation received. Closed | [12 empty] | Anoop
3 | PRIORITY HEALTH | EXTERNAL | Had PH weekly Review meeting | [12 empty] | Anoop
4 | UCARE | EXTERNAL | Worked on old ticket GCCS-48986 and shared update with the client | [12 empty] | Hari.C
5 | CARE SOURCE | EXTERNAL | Valiadated the ticket GCCS-51188 in Pre-prod instance and shared observations with the client | [12 empty] | Hari.C
6 | UCARE | EXTERNAL | Worked on old ticket GCCS-56313 and shared update with the client | [12 empty] | Hari.C
7 | PRIORITY HEALTH | INTERNAL | Had PH weekly Review meeting | [12 empty] | Anoop
8 | AHS | INTERNAL | Had Daily Stand Up Call | [12 empty] | Team
9 | UPHP | INTERNAL | Worked on GCCS-56318 and observation has been shared with the L2 team. | [12 empty] | Ambika
10 | VNS | INTERNAL | Worked on GCCS-23735/56258 and details has been shared with the internal team. | [12 empty] | Ambika
11 | MEDICA | EXTERNAL | Worked on GCCS-55985 and requested client for more details. | [12 empty] | Ambika
12 | VNS | INTERNAL | Worked on old ticket GCCS-24325 and shared the information with internal team | [12 empty] | Arun
13 | ELDER PLAN | EXTERNAL | Worked on old ticket GCCS-51248 and shared the information with the client | [12 empty] | Arun
14 | MEDICA | INTERNAL | Worked on old ticket GCCS-56329 and shared the information with internal team | [12 empty] | Arun

## 24th June
DEFECT
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
1 | CARE SOURCE | GCCS-56732 | Low | Issue | PROD: Deleted VOID Decision Row | INVESTIGATING | PS Team is working on this | DB | N | N | 8.16.2022.05 | EST | UM | N'/A | Anoop
| CARE SOURCE | GCCS-56738 | Critical | Issue | JobConnect Relation Specialist is incorrectly showing as inactive role on user accounts | INVESTIGATING | PS Team is working on this | DB/ SSO | Y | N | 8.16.2022.05 | EST | UM | C-011717 | Anoop
| MEDICA | GCCS-56739 | LOW | ISSUE | INC1122198 Member timeline not processed | INVESTIGATING | Assigned to Inbound team for further action. | INBOUND | N/A | N | 8.15.2022.06 | EST | CM | N/A | INBOUND | Ambika
| CALOPTIMA | GCCS-56769 | HIGH | ISSUE | CalOptima Preprod Auth File Load Log Report - Hourly Load | INVESTIGATING | Assigned to Inbound team for further action. | INBOUND | N/A | N | 8.13.4.2022.02 | PST | UM | N/A | INBOUND | Ambika
| ELDER PLAN | GCCS-56767 | MEDIUM | ISSUE | HEAT 277798 - Issue with Placeholder Automation on Non-English Letter Templates | IN PROGRESS | PS Team is working on this issue | Config | N | N | 8.12.2022.01 | EST | CM | N/A | PS | Arun
STORY
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
TASK
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
| CARESOURCE | GCCS-56745 | MEDIUM | TASK | SDOH Risk Configuration and 834 Integration | INVESTIGATING | Assigned to Inbound team for further action. | INBOUND | N/A | N | 8.16.2022.03 | EST | CM | N/A | INBOUND | Ambika
| MEDICA | GCCS-56740 | MEDIUM | TASK | Medica QA - Guiding Care QA portal - Password Request | WAITING FOR CUSTOMER | Requested task has been completed. | Training | N/A | N | 8.15.2022.06 | EST | CM | N/A | PS | Ambika
| VNS | GCCS-56758 | MEDIUM | TASK | Entering a Partial Approval in auth | INVESTIGATING | PS team is working on this. |  | N/A | N | 8.16.2022.05 | EST | CM | N/A | PS | Ambika
| ELDER PLAN | GCCS-56764 | MEDIUM | TASK | HEAT 278048 - Request to Add New Indicator Name Type to AD Tab in CP Section | IN PROGRESS | Assigned to DB team | DATA CHANGES | Y | N | 8.12.2022.01 | EST | CM | N/A | PS | Arun
Ad-Hocs
SL.NO | Client | Internal/ External | Description
8 | AHS | INTERNAL | Had Daily Stand Up Call | [12 empty] | Team
| AHS | INTERNAL | TECHOPS-31338: Woked on Techops with DBA Team | [12 empty] | Anoop
| AHS | INTERNAL | iTop C-011717 created and executed wrt GCCS-56738 | [12 empty] | Anoop
| MEDICA | EXTERNAL | Worked on GCCS-56650 and observation has been shared with client. | [12 empty] | Ambika

## 27th June
DEFECT
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
| VNS | GCCS-56784 | MEDIUM | ISSUE | Member Search not working for some users | INVESTIGATING | Assigned to L2 for further review |  | N/A | N | 8.16.2022.05 | EST | CM | N/A | L2 | Naresh
1 | PRIORITY HEALTH | GCCS-56789 | Medium | ISSUE | Medicare AG - Apex report is not working | INVESTIGATING | Assigned to reports team |  | N/A | N |  | EST | CM | N/A | L2 | Naresh
| CARE SOURCE | GCCS-56798 | CRITICAL | ISSUE | Guiding Care Member Eligibility not authenticating | IN CLIENT VALIDATION | Resolved | API | N/A | N | 8.16.2022.03 | EST | CM | N/A | L2-US | Anoop
| MEDICA | GCCS-56782 | CRITICAL | ISSUE | INC1123295 Appeals work queue is pulling in old/completed transaction post GC 8.15.6 Rls | INVESTIGATING | Assigned to L2 for further review |  | Y | N | 8.15.2022.06 | EST | AG | N/A | L2 | Anoop/Naresh
| PRIORITY HEALTH | GCCS-56791 | MEDIUM | ISSUE | ODAG - Medicare AG - PYMT report is not working as expcted | INVESTIGATING | Assigned to Reports Team for further review | Reports | N/A | N | 8.14.2022.03 | EST | CM | N/A | Reports | Anoop
| MEDICA | GCCS-56792 | HIGH | ISSUE | INC1123333 providers are showing as N/A on authorization summary | INVESTIGATING | Assigned to L2 for further review |  | Y | N | 8.15.2022.06 | EST | UM | N/A | L2 | Anoop
| VNS | GCCS-56778 | MEDIUM | ISSUE | Pending Activities Error Message for an Auth | INVESTIGATING | PS team is working on this. |  | Y | N | 8.16.2022.06 | EST | UM | N/A | PS | Anoop
| CARESOURCE | GCCS-56811 | LOW | ISSUE | PP1: Requesting 834 File Load | INVESTIGATING | Assigned to Inbound team for further action. | INBOUND | N/A | N | 8.16.2022.03 | EST | INBOUND | N/A | INBOUND | Ambika
| VNS | GCCS-56827 | MEDIUM | ISSUE | Duplicate Email ID ZINA McCLEAN | INVESTIGATING | Assigned to Palukuri BalaKrishna. | SSO | N/A | N | 8.16.2022.05 | EST | CM | N/A | PS | Ambika
| COA | GCCS-56823 | LOW | ISSUE | Auth Portal - Auth processed incorrectly | INVESTIGATING | PS team is working on this request. |  | N/A | N | 8.13.4.2022.01 | MST | CM | N/A | PS | Ambika
| HEALTH ALLIANCE | GCCS-56831 | CRITICAL | ISSUE | Unable to update auth priorities in PP2 | WAITING FOR CUSTOMER | Requested for more details to client. |  |  | Y | 8.14.2022.06 | EST | UM | N/A | PS | Ambika
| PRIORITY HEALTH | GCCS-56824 | CRITICAL | ISSUE | User name is showing up on member list | WAITING FOR CUSTOMER | Observation has been shared with client. |  | N | Y | 8.14.2022.03 | EST | CM | N/A | PS | Ambika
STORY
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
TASK
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
| VNS | GCCS-56806 | MEDIUM | TASK | Send historical saved PCSPs to Print queue | INVESTIGATING | PS team is working on this. | EXTRACT | N/A | N | 8.16.2022.05 | EST | CM | N/A | PS | Naresh
| DHMP | GCCS-56786 | MEDIUM | TASK | 26th edition MCG update for GC | IN PROGRESS | Assigned to Dm for further review |  | N | N | 8.11.0.M01 | MST | REPORTS | N/A | DM | Naresh
| CARE SOURCE | GCCS-56795 | MEDIUM | TASK | 2022_06_28 Prod Deploy Request | OPEN | Assigned to L2 for further review | Sync Task | N/A | N | 8.16.2022.03 | EST | CM | N/A | L2 | Anoop
| EASTPOINTE | GCCS-56781 | MEDIUM | TASK | Health Indicators - Configuration Question | Open | Assigne to BA for further review | Configuration | N/A | N | 8.16.2022.05 | EST | CM | N/A | BA | Anoop
| MedStar | GCCS-56780 | MEDIUM | TASK | Historical Auth Load Single baby | OPEN | Assigned to Inbound Team | DataLoads | N/A | N | 8.15.2022.05 | EST | CM |  | Inbound | Anoop
| HEALTH ALLIANCE | GCCS-56812 | MEDIUM | TASK | New ProgramEnrollment file into GC | INVESTIGATING | Assigned to Inbound team for further action. | INBOUND | N/A | N | 8.14.2022.03 | EST | INBOUND | N/A | INBOUND | Ambika
| VNS | GCCS-56815 | MEDIUM | TASK | Outbound Interface logic for HHAX | INVESTIGATING | Assigned to Avinash Sagi. | OUTBOUND | N/A | N | 8.16.2022.05 | EST | OUTBOUND | N/A | OUTBOUND | Ambika
| VNS | GCCS-56814 | MEDIUM | TASK | Inbound Eligibility load issue | INVESTIGATING | Assigned to Avinash Sagi. | INBOUND | N/A | N | 8.16.2022.05 | EST | OUTBOUND | N/A | INBOUND | Ambika
Ad-Hocs
SL.NO | Client | Internal/ External | Description
internal call
| MEDICA | EXTERNAL | Worked on GCCS-22186 and requested task has been completed. | [12 empty] | Ambika
| VNS | INTERNAL | Worked on GCCS-56758 and details has been shared with the internal team. | [12 empty] | Ambika

## 28th June
DEFECT
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
1 | CARESOURCE | GCCS-56857 | High | Issue | G&A Letter FICO rule not executing | Investigating | Assigned to Rules Team | Rules | N/A | N | 8.16.2022.03 | EST | AG | N/A | RULES | Anoop
| CARESOURCE | GCCS-56848 | Critical | Issue | PROD : GC giving 503 errors | In Client Review | Issue resolved. Team is working on the RCA | SSO/OKTA | Y | N | 8.16.2022.03 | EST | CM | N/A | L0/DEVOPS | Anoop
| ICIRCLE | GCCS-56860 | Critical | Issue | Critical Data Issue - Provider Information | INVESTIGATING | Assigned toDBA Team for further Action | DBA | N/A | N | 8.13.4.2022.05 | EST | CM | N/A | DBA | Anoop
| CARESOURCE | GCCS-56866 | LOW | ISSUE | G&A Auto Ack FICO rule only picked up 4 | INVESTIGATING | Assigned to rules team for further action. | FICO Rules | N/A | N | 8.16.2022.03 | EST | RULES | N/A | RULES | Ambika
| HEALTH ALLIANCE | GCCS-56896 | MEDIUM | ISSUE | Batch configuration change | IN PROGRESS | Assigned to L2 team | Config | N | N | 8.14.2022.03 | EST | UM | N/A | SWAT INDIA | Arun
| CARE SOURCE | GCCS-56879 | LOW | ISSUE | Prod: member load exceptions for specific plan | IN PROGRESS | Assigned to Inbound Team | INBOOUND | N | N | 8.16.2022.03 | EST | INBOUND | N/A | INBOUND | Arun
STORY
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
| CARESOURCE | GCCS-56865 | MEDIUM | STORY | UM - Do not prevent UM Internal Scripts in one auth due to a pending script in another auth | OPEN | Assigned to Deepak Sharma | Enhancement | N/A | N | 8.16.2022.03 | EST | UM | N/A | DM | Ambika
TASK
SL.No | Client | Source ID | Priority | Fix Type | Description | Status | Issue Resolution/PS Comments | Expected FixType | Reproduced | Need More Details | Version | Time Zone | Module | iTop ID | Team
| CARESOURCE | GCCS-56864 | Medium | Task | UM - Prevent UM auth from being closed when there is a pending Internal Script for the auth | Investigating | PS Team is working on this |  | N/A | N | 8.16.2022.03 | EST | UM | N/A | PS | Anoop
| MedStar | GCCS-56859 | Medium | Task | Request to remove extra 'Referred To Provider Name' from letter template | Open | Assigned to Letters Team | Letters | N/A | N | 8.15.2022.05 | EST | CM | N/A | Letters | Anoop
| PRIORITY HEALTH | GCCS-56843 | Medium | Task | API Credentials Pulse | Open | Assigned to Devops Team | API | N/A | N | 8.14.2022.03 | EST | API | N/A | DEVOPS | Anoop
| MEDICA | GCCS-56841 | Medium | Task | Please remove this individual’s Tableau access, they are no longer with Medica, thanks. | Closed | Task Completed | Tableau | N/A | N | 8.15.2022.06 | EST | Reports | N/A | Tableau | Anoop
| MEDICA | GCCS-56846 | Medium | Task | Question: What is the File Size Limit for attachments in Guiding Care? | In Client Review | Waiting for Client feed | DB | N/A | N | 8.15.2022.06 | EST | CM | N/A | PS | Anoop
| MedStar | GCCS-56851 | Medium | Task | Add Dropdowns in CM Module | Investigating | PS Team is working on this |  | N/A | N | 8.15.2022.05 | EST | CM | N/A | PS | Naresh
| DHMP | GCCS-56852 | MEDIUM | TASK | Changing eligibility after auth creation | In Client Review | Waiting for Client feed | TRAINING | N | N | 8.11.0.M01 | MST | UM | N/A | PS | Naresh
| UPHP | GCCS-56868 | MEDIUM | TASK | Delete Consent Forms | INVESTIGATING | PS team is working on this. | DB |  | N | 8.14.2022.02 | EST | CM | N/A | PS | Naresh
| HEALTH ALLIANCE | GCCS-56875 | MEDIUM | TASK | SSO for existing user | INVESTIGATING | PS team is working on this request. | SSO | N/A | N | 8.14.2022.06 | EST | CM | N/A | PS | Ambika
| VNS | GCCS-56873 | MEDIUM | TASK | New Process to auto import PDFs and upload to new document type | INVESTIGATING | Assigned to Inbound team for further action. | INBOUND | N/A | N | 8.16.2022.05 | EST | INBOUND | N/A | INBOUND | Ambika
| PRIORITY HEALTH | GCCS-56876 | MEDIUM | TASK | Copy Medical ODAG Reports into PreProd from Prod | INVESTIGATING | Assigned to reports team for further action. | Reports | N/A | N | 8.14.2022.03 | EST | TABLEAU | N/A | REPORTS | Ambika
| CALOPTIMA | GCCS-56871 | MEDIUM | TASK | CM Health Note types added not showing in Dropdown | INVESTIGATING | PS team is working on this request. | Configuration | N/A | N | 8.13.4.2022.02 | PST | CM | N/A | PS | Ambika
| MEDICA | GCCS-56884 | MEDIUM | TASK | Convert from Shared Content to a Form in SmartComm and place in proper directory | IN PROGRESS | PS Team is working on this task | Data Changes | N | N | 8.15.2022.02 | EST | LETTERS | N/A | PS | Arun
Ad-Hocs
SL.NO | Client | Internal/ External | Description
| AHS | INTERNAL | Had CCB Call | [12 empty] | Anoop
| COA | INTERNAL | Worked on GCCS-56823 and details has been shared with the internal team. | [12 empty] | Ambika
| HAMP | INTERNAL | Worked on GCCS-56831 and details has been shared with the L2 team. | [12 empty] | Ambika